## Project Plan Template
Instructional Design Team
2023 EMPATHY TRAINING PROGRAM - PROJECT PLAN
| PROJECT TITLE |  | START DATE
| Empathy Training Program |  | 2023-01-02 |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  | in hours | in days
Ana Grade |  |  | 2023-04-21 |  | 640 | 80
Task # | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in hours | DURATION in days | COMMENTS | STATUS
1 | Milestone: Analysis Phase |  |  | 2023-01-02 | 2023-01-13 | 80 | 10 |  | Not Started
1.1 | Conduct research on empathy training needs and best practices | Complete | anagrade | 2023-01-02 | 2023-01-02 | 8 | 1 |  | In Progress
1.2 | Develop training objectives and learning outcomes | Complete | anagrade | 2023-01-03 | 2023-01-03 | 8 | 1 |  | Complete
1.3 | Determine target audience and delivery method | Complete | anagrade | 2023-01-04 | 2023-01-04 | 8 | 1 |  | On Hold
1.4 | Create Project Plan | Complete | anagrade | 2023-01-05 | 2023-01-05 | 8 | 1
1.5 | Create Narrative Proposal | Complete | anagrade | 2023-01-06 | 2023-01-13 | 48 | 6
2 | Milestone: Design Phase |  |  | 2023-01-16 | 2023-03-03 | 280 | 35
2.1 | Create content outline for Module 1, Module 2 and Module 3 | Complete | anagrade | 2023-01-16 | 2023-01-18 | 24 | 3 | Martin Luther King Holiday Impact
2.2 | Create content outline for Module 4, Module 5, Module 6 and Module 7 | Complete | anagrade | 2023-01-19 | 2023-01-24 | 32 | 4
2.3 | Create content outline for Module 7, Module 8 and Module 9 | Complete | anagrade | 2023-01-31 | 2023-02-06 | 40 | 5
2.4 | Stakeholder review of training content outline | In Progress | anagrade | 2023-02-13 | 2023-02-24 | 80 | 10
2.6 | Apply stakeholder feedback and deliver final version of all outlines | Not Started | anagrade | 2023-02-27 | 2023-03-03 | 40 | 5
3 | Milestone: Development Phase |  |  | 2023-02-13 | 2023-04-03 | 288 | 36
3.1 | Develop SDL Module 1: What's Empathy? | Not Started | anagrade | 2023-02-13 | 2023-02-14 | 16 | 2
3.2 | Develop SDL Module 2: Empathy vs Sympathy | Not Started | anagrade | 2023-02-15 | 2023-02-17 | 24 | 3
3.3 | Develop SDL Module 3: Emotional Intelligence | Not Started | anagrade | 2023-02-20 | 2023-02-22 | 24 | 3
3.4 | Develop SDL Module 4: Acitve Listening | Not Started | anagrade | 2023-03-06 | 2023-03-08 | 24 | 3
3.5 | Develop SDL Module 5: Manage Tone of Voice | Not Started | anagrade | 2023-03-09 | 2023-03-13 | 24 | 3
3.6 | Develop SDL Module 6: Apologize and Acknowledge | Not Started | anagrade | 2023-03-14 | 2023-03-16 | 24 | 3
3.7 | Develop SDL Module 7: Demonstrating Ownership and Paraphrasing | Not Started | anagrade | 2023-03-17 | 2023-03-21 | 24 | 3
3.8 | Develop SDL Module 8: Practicing Empathy | Not Started | anagrade | 2023-03-22 | 2023-03-24 | 24 | 3
3.9 | Develop SDL Module 9: Empathy Barriers | Not Started | anagrade | 2023-03-27 | 2023-03-29 | 24 | 3
3.1 | Develop SDL Module 9: Maintaining Empathy in High-Stress Situations | Not Started | anagrade | 2023-03-30 | 2023-04-03 | 24 | 3
4 | Milestone: Implementation Phase |  |  | 2023-04-03 | 2023-05-01 | 168 | 21
4.1 | Peer Review - Modules 1 to 9 | Not Started | anagrade | 2023-04-03 | 2023-04-07 | 40 | 5
4.2 | Stakeholder review of Modules 1 to 9 | Not Started | Logins | 2023-04-03 | 2023-04-07 | 40 | 5
4.3 | Implementation of Stakeholder and Peer Feedback | Not Started | Operations | 2023-04-10 | 2023-04-12 | 24 | 3
4.4 | Build Curriculum in LMS | Not Started | anagrade | 2023-04-13 | 2023-04-17 | 24 | 3
4.5 | Test Curriculum in LMS | Not Started | anagrade | 2023-04-18 | 2023-04-19 | 16 | 2
4.6 | Publish Final Version of Curriculum in LMS | Not Started | anagrade | 2023-05-01 | 2023-05-01 | 8 | 1
5 | Milestone: Evaluation Phase |  |  | 2023-05-15 | 2023-05-19 | 40 | 5
5.1 | Review and analyze results of assessments and evaluations | Not Started | anagrade | 2023-05-15 | 2023-05-19 | 40 | 5 | This dates may change as it depends on NHT class schedule.
5.2 | Create report of findings and recommendations for improvement | Not Started | anagrade | 2023-05-22 | 2023-05-26 | 40 | 5 | This dates may change as it depends on NHT class schedule.
5.4 | Present final report to stakeholders | Not Started | anagrade | 2023-05-29 | 2023-05-29 | 8 | 1 | This dates may change as it depends on NHT class schedule.
5.5 | Create Q3/Q4 Plan to improve program | Not Started | anagrade | 2023-05-30 | 2023-05-31 | 16 | 2 | This dates may change as it depends on NHT class schedule.
Formulas:
in days = NETWORKDAYS(E4,[END DATE])
DURATION in days = NETWORKDAYS([START DATE],[in hours])