## CP07-C4C5C6 Sheet-1
Table 1 - Executive Summary |  | As of 27 July 2023 | Table 2 - Top Critical Issues Programme wide |  |  |  | Table 3 - EOT Statistics
BP | Key Achievements |  | Critical Issues | Mitigation Plan | Impact | Action By | Action with | Numbers
CP07-C4C5C6 | Contract completion 04 May 2023 expired. Contractor claimed EOT until 02 February 2024. LREDC offered EOT until 24 October 2023. Contractor yet to confirm acceptance. Contractor verbally informed they will resubmit the EOT request including updated events. |  | Delays to Western Gateway construction activities impacting the Overall Completion date. | The remaining works can be rescheduled to complete within the extended Completion date. | High | 2023-07-01 | CONTRACTOR TO RESUBMIT/RESPOND | 0
CP07-C4C5C6 |  |  | Contractor’s delay in procurement | The remaining procurement & installation works can be rescheduled to complete within the extended Completion date. | High | 2023-07-01 | WITH - PMCM | 0
CP07-C4C5C6 |  |  | Concerns on the quality of executed hardscape works | AJP to endorse NCRs/SORs issued by CSC. Handover inspections commenced with the CSC. Contractor to endorse the snags. | Medium | 2023-07-01 | WITH - LREDC | 1
CP07-C4C5C6 | [6 empty] | GLOBAL SETTLEMENT | 0
[7 empty] | EOT CLAIM CLOSED (awarded/rejected) | 2
[7 empty] | Total Number of EOT's Claimed | 3
[7 empty] | Number of Ongoing EOT Reviews | 1

## CP07-C4C5C6 Sheet-2
Table 4 - Top 5 Programme Wide Risks |  |  |  |  | Table 7 - KPI Data |  | As of 27 July 2023
Risk Description | Likelihood (H/M/L) | Severity (H/M/L) | Mitigation Measure | Identified on |  | Planned Progress % | Actual Progress %
Delays to Western Gateway construction activities impacting the Overall Completion date. | 5 | 4 | LREDC offered EOT until 24 October 2023. Subject to acceptance by the Contractor, the remaining works can be rescheduled to complete within the extended Completion date. | 2022-09-01 | Project Wide | 100% | 92.16%
Contractor’s delay in procurement | 5 | 4 | LREDC offered EOT until 24 October 2023. Subject to acceptance by the Contractor, the remaining procurement & installation works can be rescheduled to complete within the extended Completion date. | 2022-09-01
Concerns on the quality of executed hardscape works | 4 | 4 | AJP to endorse NCRs/SORs issued by CSC. Handover inspections commenced with the CSC. Contractor to endorse the snags. | 2022-09-01
Table 5 - Not used |  | Table 6 - Key Events
- Contract completion 04 May 2023 expired. Contractor claimed EOT until 27 May 2024. PIL recommended rejection

## CP07A3 Sheet-1
Table 1 - Executive Summary |  | As of 27 Jul 2023 | Table 2 - Top Critical Issues Programme wide |  |  |  | Table 3 - EOT Statistics
BP | Key Achievements |  | Critical Issues | Mitigation Plan | Impact | Action By | Action with | Numbers
CP07-A3 | Works in Road A1 south and Junction Completed |  | Open works to be addressed by the Contractor | The Contractor has open works where he can address and complete the progress by deploying additional manpower | High | 2023-07-01 | CONTRACTOR TO RESUBMIT/RESPOND | 0
CP07-A3 | Contractor is proceeding with completion of softscaping & irrigation works in Seef North, Road A1 |  | Delay in delivery of materials | Contractor must expedite the procurement process | High | 2023-07-01 | WITH - PMCM | 1
CP07-A3 | Softscaping in progress for LI13 work | [5 empty] | WITH - LREDC | 0
[7 empty] | GLOBAL SETTLEMENT | 0
[7 empty] | EOT CLAIM CLOSED (awarded/rejected) | 5
[7 empty] | Total Number of EOT's Claimed | 6
[7 empty] | Number of Ongoing EOT Reviews | 1

## CP07A3 Sheet-2
Table 4 - Top 5 Programme Wide Risks |  |  |  |  | Table 7 - KPI Data |  | As of 27 Jul 2023
Risk Description | Likelihood (H/M/L) | Severity (H/M/L) | Mitigation Measure | Identified on |  | Planned Progress % | Actual Progress %
Procurement / Long Lead Items: Risk of affecting the critical path due to procurement delays. Project Completion Delay risk. | H | H | Procurement to be closely monitored. | 2021-03-01 | Project Wide | 100% | 95.81%
Possibility of Variations affecting the project Completion | H | H | Variations if any, to be issued to the Contractor at the earliest | 2021-03-01
Table 5 - Not used |  | Table 6 - Key Events
Contractor requested completion certificate with outstanding works to be accomplished during Guarantee period. PIL recommended the completion certificate as of 31 July 2023 and currently under review with LREDC

## CP10G1 Sheet-1
Table 1 - Executive Summary |  | As of 27 Jul 2023 | Table 2 - Top Critical Issues Programme wide |  |  |  | Table 3 - EOT Statistics
BP | Key Achievements |  | Critical Issues | Mitigation Plan | Impact | Action By | Action with | Numbers
| Majority of works completed in Wadi Park & Fox hills J26b |  | Contractor is delayed in material submittals and procurement | Contractor must expedite the procurement process | High | 2023-07-01 | CONTRACTOR TO RESUBMIT/RESPOND
| Softscaping work in progress in for CP10G1 |  | Contractor is behind schedule | Contractor must expedite the softscape and hardscape works in CP10G1 | High | 2023-07-01 | WITH - PMCM
| Snagging Ongoing in Foxhills Parkings | [5 empty] | WITH - LREDC | 1
GLOBAL SETTLEMENT
[7 empty] | EOT CLAIM CLOSED (awarded/rejected) | 3
[7 empty] | Total Number of EOT's Claimed | 4
[7 empty] | Number of Ongoing EOT Reviews | 1

## CP10G1 Sheet-2
Table 4 - Top 5 Programme Wide Risks |  |  |  |  | Table 7 - KPI Data |  | As of 27 Jul 2023
Risk Description | Likelihood (H/M/L) | Severity (H/M/L) | Mitigation Measure | Identified on |  | Planned Progress % | Actual Progress %
Completion of Al Khuzama Park | M | M | The Contractor must take necessary action to ensure the works are completed as per CA1 | 2022-11-22 | Project Wide | 100% | 92.85%
Table 5 - Not used |  | Table 6 - Key Events
Contractor requested completion certificate with outstanding works to be accomplished during Guarantee period. PIL recommended the completion certificate as of 31 July 2023 and currently under review with LREDC

## EOT summary
Project Name | Package Name | Basis of Claim | Claimant | Original Contract Start Date | Original Contract Completion Date | Revised Contract Completion Date | EOT No | Designer / Contractor Requested Finish Date | PMC Recommended - Finish Date | Client Recommended Finish Date | Contractor's Potential EOT Entitlement Date | Designer / Contractor submission date | PMC Review Finish Date | LREDC OTHERS (EOT Offer/ response Issue Date) | EOT OFFER ACCEPTANCE/ RESPONSE | Revised Completion with EOT | CURRENT STATUS
PJ1 | Landscape Works for Seef Lusail | Potable Water Network | AJP | 2020-03-22 | 2022-02-19 |  | 1 | 2022-12-17 | 2022-11-10 | 2022-11-10 | 2022-11-10 | 2022-06-06 | 2022-06-19 | 2022-06-28 | Accepted | 2022-11-10 | Closed
PJ1 | Landscape Works for Seef Lusail | Impact of SI | AJP | 2020-03-22 | 2022-02-19 | 2022-11-10 | 2 | 2023-03-29 | 2023-03-13 | 2023-03-13 | 2023-03-13 | 2022-10-20 | 2022-10-31 | 2022-11-06 | Accepted | 2023-03-13 | Closed
PJ1 | Landscape Works for Seef Lusail | FIFA stoppage | AJP | 2020-03-22 | 2022-02-19 | 2023-03-13 | 3 | 2023-08-15 | 2023-06-28 | 2023-06-28 | 2023-06-28 | 2023-03-08 | 2023-03-20 | 2023-04-02 | Not accepted by Contractor |  | Contractor did not accept
PJ1 | Landscape Works for Seef Lusail | Obstructions | AJP | 2020-03-22 | 2022-02-19 | 2023-03-13 | 4 | 2023-12-02 | 2023-10-21 | Under Review | Under Review | 2023-06-26 | 2023-07-06 | Under review | Under review |  | Under Review
PJ3 | Landscape works for Commercial Boulevard on Road A4, Linear Parks and Road A3 & D3 | KMA approvals | AJP | 2020-06-01 | 2022-07-30 |  | 1 | 2023-07-26 | 2023-05-04 | 2023-05-04 | 2023-05-04 | 2022-05-05 | 2022-05-18 | 2022-05-26 | Accepted | 2023-05-04 | Closed
PJ3 | Landscape works for Commercial Boulevard on Road A4, Linear Parks and Road A3 & D3 | Obstructions in Road E22 | AJP | 2020-06-01 | 2022-07-30 | 2023-05-04 | 2 | 2024-02-02 | 2023-10-24 | 2023-10-24 | Contractor did not accept |  |  | 2023-05-02 | Contractor did not accept | 2023-05-04 | Closed. Not accepted by Contractor
PJ3 | Landscape works for Commercial Boulevard on Road A4, Linear Parks and Road A3 & D3 | FIFA restrictions | AJP | 2020-06-01 | 2022-07-30 | 2023-05-04 | 2 | 2024-05-27 | Under Review | Under Review | Under Review | 2023-07-10 | 2023-07-18 | Under review | Under review | 2023-05-04 | Under Review
PJ2 | Landscape Works for Waterfront Residential | Impact of SI | LWX | 2022-01-23 | 2023-01-22 |  | 1 | 2023-05-22 | 2023-04-20 | 2023-04-20 | 2023-04-20 | 2022-11-09 | 2022-11-17 | 2022-11-20 | Accepted | 2023-04-20 | Closed.
PJ2 | Landscape Works for Waterfront Residential | Impact of SI | LWX | 2022-01-23 | 2023-01-22 | 2023-04-20 | 2 | 2023-08-22 | 2023-07-03 | 2023-07-03 | 2023-07-03 | 2023-04-04 | 2023-04-17 | 2023-05-03 | Accepted | 2023-07-03 | VO under signature
PJ2 | Landscape Works for Waterfront Residential - CVF01 Khuzama Park | Design Changes | LWX | 2022-11-09 | 2023-03-28 |  | 1 | 2023-06-21 | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2023-04-17 | 2023-05-01 | 2023-05-08 | Accepted | 2023-06-12 | VO under signature
PJ2 | Landscape Works for Waterfront Residential | KMA approvals | LWX | 2022-01-23 | 2023-01-22 | 2023-07-03 | 3 | 2023-09-20 | 2023-08-24 | Under Review | Under Review | 2023-06-27 | 2023-07-10 | Under review | Under review |  | Under Review

## EOT summary_BP25
Sr.No | CP/BP.No | Package Name | Claimant | Original Contract Start Date | Original Contract Completion Date | Revised Contract Completion Date | EOT No | Designer / Contractor Requested Finish Date | PMCM Recommended - Finish Date | LREDC Recommended Finish Date | Contractor's Potential EOT Entitlement Date | Designer / Contractor submission date | PM/CM Review Finish Date | LREDC PM Review Finish | LREDC PLANNING Response Date | LREDC OTHERS (EOT Offer/ response Issue Date) | EOT OFFER ACCEPTANCE/ RESPONSE | CVF ISSUANCE DATE BY LREDC TO CONTRACTOR | Revised Completion with EOT | CURRENT STATUS | Currently in Action with
1 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-07-01 | - | - | - | 2020-07-11 |  |  |  | 2020-09-17 | Rejected |  |  | Rejected | Closed
2 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-06-05 | - | - | - | 2020-07-20 | 2020-07-30 |  |  | 2020-09-17 | Rejected |  |  | Rejected | Closed
3 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-07-26 | - | - | - | 2020-07-25 | 2020-07-30 |  |  | 2020-09-13 | Rejected |  |  | Rejected | Closed
4 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-07-01 | - | - | - | 2020-08-27 | 2020-11-20 |  |  | 2020-11-20 | Rejected |  |  | Rejected | Closed
5 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-07-26 | - | - | - | 2020-09-16 | 2020-09-30 |  |  | 2020-11-08 | Rejected |  |  | Rejected | Closed
6 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-08-07 | - | - | - | 2020-11-11 | 2020-12-20 |  |  | 2021-01-28 | Rejected |  |  | Rejected | Closed
7 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-08-07 | - | - | - | 2020-11-11 | 2020-12-20 |  |  | 2021-01-28 | Rejected |  |  | Rejected | Closed
8 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-10-24 | - | - | - | 2021-01-11 | 2021-01-21 |  |  | 2021-01-26 | Rejected |  |  | Rejected | Closed
9 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-07-26 | 2021-07-22 | - | - | 2021-02-08 | 2021-02-08 |  |  | 2021-02-28 | Rejected |  |  | Rejected | Closed
10 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-09-29 | - | - | - | 2021-02-14 | 2021-03-02 |  |  | 2021-03-07 | Rejected |  |  | Rejected | Closed
11 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  |  | 2021-10-27 | - | - | - | 2021-03-11 | 2021-03-30 |  |  | 2021-04-05 | Rejected |  |  | Rejected | Closed
12 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 |  | 1 | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-07-26 | 2021-03-13 | 2021-03-16 |  |  | 2021-03-30 | Accepted | 2021-06-02 | 2021-07-26 | Closed | Closed
13 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 | 2021-07-26 |  | 2022-01-07 | - | - | - | 2021-04-17 | 2021-04-25 |  |  | 2021-05-31 | Rejected |  |  | Rejected | Closed
14 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 | 2021-07-26 |  | 2022-01-07 | - | - | - | 2021-08-01 | 2021-09-30 |  |  | 2021-11-09 | Rejected |  |  | Rejected | Closed
15 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 | 2021-07-26 | 2 | 2021-12-30 | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-08-24 | 2021-09-06 |  |  | 2021-09-19 | Accepted | 2021-11-25 | 2021-11-01 | Closed | Closed
16 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | UCC | 2019-05-13 | 2021-05-12 | 2021-11-01 |  | 2022-07-27 | - | - | - | 2021-09-19 | 2021-09-30 |  |  | 2021-11-09 | Accepted | 2021-11-25 |  | Closed | Closed
17 | BP25.3 | Construction of Seef Lusail Development Project in Plot D1D2 | Settlement Agreement | 2019-05-13 | 2021-05-12 | 2021-11-01 | 3 |  |  | 2022-05-31 | [5 empty] | 2022-03-16 | Accepted | 2022-04-17 | 2022-05-31 | Closed | Closed
BP25.4
1 | BP25.4 | Construction of Seef Lusail Development Project in Plot D3D4 | UCC | 2019-05-13 | 2021-12-12 |  |  | 2022-03-10 | - | - | - | 2021-06-19 | 2021-06-24 |  |  | 2021-08-08 | Rejected |  |  | Rejected | Closed
2 | BP25.4 | Construction of Seef Lusail Development Project in Plot D3D4 | UCC | 2019-05-13 | 2021-12-12 |  |  | 2022-01-21 | - | - | - | 2021-08-16 | 2021-09-02 |  |  | 2021-09-08 | Rejected |  |  | Rejected | Closed
3 | BP25.4 | Construction of Seef Lusail Development Project in Plot D3D4 | UCC | 2019-05-13 | 2021-12-12 |  |  | 2022-03-10 | - | - | - | 2021-09-13 | 2021-09-21 |  |  | 2021-10-26 | Rejected |  |  | Rejected | Closed
4 | BP25.4 | Construction of Seef Lusail Development Project in Plot D3D4 | UCC | 2019-05-13 | 2021-12-12 |  |  | 2022-03-10 | - | - | - | 2021-12-21 | 2021-12-26 |  |  | 2022-02-02 | Rejected |  |  | Rejected | Closed
5 | BP25.4 | Construction of Seef Lusail Development Project in Plot D3D4 | UCC | 2019-05-13 | 2021-12-12 |  |  | 2022-02-20 | - | - | - |  | 2020-10-05 |  |  | 2020-10-21 | Rejected |  |  | Rejected | Closed
6 | BP25.4 | Construction of Seef Lusail Development Project in Plot D3D4 | Settlement Agreement | 2019-05-13 | 2021-12-12 |  | 1 |  |  | 2022-08-31 | [5 empty] | 2022-03-16 | Accepted | 2022-04-17 | 2022-08-31 | Closed | Closed
Formulas:
PMCM Recommended - Finish Date = +[Original Contract Completion Date, row above]+71
PMCM Recommended - Finish Date = +[Revised Contract Completion Date]+98
LREDC Recommended Finish Date = +[PMCM Recommended - Finish Date]
LUSAIL BUILDING PROJECTS: EOT LOG
As of 27 Jul 2023

## Progress
LUSAIL BUILDINGS MASTER PROGRAMME Rev. 01 - Update @ 27-Jul-23
Work Description |  | Plan % | Actual % | Start | Finish | Remarks
BP-25 : Seef Lusail Development
Activation Plan
BP-25-03: Seef Lusail - D1 & D2 (Mix Use - Residential)
| BP25-03-B: Construction work | 100% | 99.9% | 2019-05-13 | 2022-09-21 | Completion certificate issued
BP-25-04: Seef Lusail - D3 & D4 (Mix Use - Residential)
| BP25-04-B: Construction work | 100% | 99.82% | 2019-05-13 | 2023-09-30 | Completion certificate request with 17-Nov-22 as completion rejected by LREDC. MOI approval received. Awaiting Marafeq approval for D4 and LCAC clerance to isuue BCC. Expected by end of Sep 2023
BP-25-01: Seef Lusail - A3a (Presentation Center)
| Construction - Main Work | 100% | 100% | 2015-06-03 | 2021-01-19
Landscape Packages
CP07-A3 - Waterfront Commercial//Seef Lusail - Public Realm
| Procurement of Contractor |  |  | 2019-08-27 | 2020-02-29
| Construction works | 100% | 95.81% | 2020-03-22 | 2023-11-30 | Forecast date pushed due to non-planting season. Contractor requested completion certificate with outstanding items to be done during Guarantee Period
CP07-C4 -Commercial Boulevard Linear Parks
| Procurement of Contractor |  |  | 2019-10-03 | 2020-05-10
| Construction works | 100% | 92.16% | 2020-06-01 | 2024-01-24 | Contractor requested EOT upto 27 May 2024. Currently under review with LREDC
CP10-G1 - Waterfront Residential Parks
| Procurement of Contractor |  |  | 2021-04-15 | 2022-01-22
| Construction works | 100% | 92.85% | 2022-01-23 | 2023-09-20 | Contractor requested completion certificate with outstanding items to be done during Guarantee Period