## PM
Project Name | Project Manager | Contractor | Project Title | Start Date | Original Finish | Original Duration | Revised Finish | Revised Finish | Duration Elapased
PJ1 | Mike | Best Contractor WLL | Infraworks in North | 2020-05-22 | 2022-02-19 | 639 | 2023-03-13 | 1026 | 1172
PJ2 | Mohd | World Class Projects | Waterfront project in Doha South | 2022-06-23 | 2023-01-22 | 214 | 2023-07-03 | 376 | 410
PJXX | Steve | SPLL | Construction of G+60 towers | 2019-05-01 | 2021-06-12 | 774 | 2022-05-31 | 1127 | 1559
PJXXX | Kumar | EPC company | Construction of G+4P+50 towers | 2019-05-01 | 2021-12-30 | 975 | 2022-07-31 | 1188 | 1559
PJ3 | Ricky | SPLL | Sewage Development | 2020-06-01 | 2022-07-31 | 791 | 2023-05-31 | 1095 | 1162
Formulas:
Duration Elapased = TODAY()-[Start Date]

## PJ3
Project ID | Date | Original Plan% | Original Act % | Rev.1 Plan% | Rev.1 Act % | Rev.2 Plan% | Rev.2 Act % | Variance % (Act-Plan) | Forecast Completion | No. of days delayed | Planned Manpower | Actual Manpower | Mandays | Total Manhours | Total Manhours after LTI | HSE NCR Issued to Date | HSE NCRs Closed | HSE NCRs Open | Engineering: Baseline : Planned % | Engineering: Actual % | Procurement : Baseline : Planned % | Procurement : Actual % | Construction works : Baseline : Planned % | Construction works : Actual % | Commissioning/ Snagging : Baseline : Planned % - | Commissioning/ Snagging : Actual % - | R1 - Risk Description | R1 - Risk Mitigation | R1 - Action by | R1 - Status | R2- Risk Description | R2- Risk Mitigation | R2- Action by | R2- Status | R3- Risk Description | R3- Risk Mitigation | R3- Action by | R3- Status | Change Requests Issued to Contractor | CR Provided Cost & Time Impacts by Contractor | CR Under Client Review | CR Agreed by both paries | CRNot accepted | Variation Issued to Contractor | Variation Provided Cost & Time Impacts by Contractor | Variation Under Client Review | Variation Agreed by both paries | Variation Not accepted | SI | Si Issued to Contractor | SI Provided Cost & Time Impacts by Contractor | SIUnder Client Review | SI Agreed by both paries | SI Not accepted | Project cost - Original | Variations approved | Net Total Invoice requested | Net Total Paid to date | Net Certified to date | Payment remaining | Estimate at completion | Top Driving Item 1 | Top Driving Item 2 | Top Driving Item 3
PJ3 | 2020-03-27 | 0% | 0% | 0% | 0% |  |  | 0% | 2022-07-30 | 0 | 0 | 18 |  |  |  | 0 | 0 | 0
PJ3 | 2020-04-03 | 0% | 0% | 0% | 0% |  |  | 0% | 2022-07-30 | 0 | 0 | 18 |  |  |  | 0 | 0 | 0
PJ3 | 2020-04-10 | 0% | 0% | 0% | 0% |  |  | 0% | 2022-07-30 | 0 | 0 | 18 |  |  |  | 0 | 0 | 0
PJ3 | 2020-04-17 | 0% | 0% | 0% | 0% |  |  | 0% | 2022-07-30 | 0 | 0 | 32 |  |  |  | 0 | 0 | 0
PJ3 | 2020-04-24 | 0% | 0% | 0% | 0% |  |  | 0% | 2022-07-30 | 0 | 0 | 44 |  |  |  | 0 | 0 | 0
PJ3 | 2020-05-01 | 0% | 0% | 0% | 0% |  |  | 0% | 2022-07-30 | 0 | 0 | 44 |  |  |  | 0 | 0 | 0
PJ3 | 2020-05-08 | 0% | 0% | 0% | 0% |  |  | 0% | 2022-07-30 | 0 | 0 | 46 |  |  |  | 0 | 0 | 0
PJ3 | 2020-05-15 | 0% | 0% | 0% | 0% |  |  | 0% | 2022-07-30 | 0 | 0 | 45 |  |  |  | 0 | 0 | 0
PJ3 | 2020-05-22 | 0% | 0% | 0% | 0% |  |  | 0% | 2022-07-30 | 0 | 0 | 45 |  |  |  | 0 | 0 | 0
PJ3 | 2020-05-29 | 0% | 0% | 0% | 0% |  |  | 0% | 2022-07-30 | 0 | 0 | 45 |  |  |  | 0 | 0 | 0
PJ3 | 2020-06-05 | 0% | 3.613e-05% | 0% | 3.613e-05% |  |  | 3.613e-05% | 2022-07-30 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0% | 0.001774% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-06-12 | 0% | 0.00106% | 0% | 0.00106% |  |  | 0.00106% | 2022-07-30 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0% | 0.01005% | 0% | 0% | 0% | 0.001% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-06-19 | 0% | 0.003156% | 0% | 0.003156% |  |  | 0.003156% | 2022-07-30 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0% | 0.06573% | 0% | 0% | 0% | 0.002125% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-06-26 | 0% | 0.006487% | 0% | 0.006487% |  |  | 0.006487% | 2022-07-30 | 0 | 0 | 46 |  |  |  | 0 | 0 | 0 | 0% | 0.182% | 0% | 0% | 0% | 0.00325% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-07-03 | 0% | 0.01053% | 0% | 0.01053% |  |  | 0.01053% | 2022-07-30 | 0 | 18 | 57 |  |  |  | 0 | 0 | 0 | 0% | 0.307% | 0% | 0% | 0% | 0.005% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-07-10 | 0.0863% | 0.06259% | 0.0863% | 0.06259% |  |  | -0.02372% | 2022-07-30 | 0 | 18 | 58 |  |  |  | 0 | 0 | 0 | 0% | 0.4327% | 0% | 0% | 0.1009% | 0.06287% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-07-17 | 0.1726% | 0.1646% | 0.1726% | 0.1646% |  |  | -0.007993% | 2022-07-30 | 0 | 18 | 58 |  |  |  | 0 | 0 | 0 | 0% | 0.5576% | 0% | 0.03047% | 0.2018% | 0.1762% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-07-24 | 0.2717% | 0.2697% | 0.2717% | 0.2697% |  |  | -0.00204% | 2022-07-30 | 0 | 18 | 58 |  |  |  | 0 | 0 | 0 | 0.009098% | 0.6827% | 0.1529% | 0.15% | 0.3027% | 0.2845% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-07-31 | 0.3772% | 0.3906% | 0.3772% | 0.3906% |  |  | 0.01338% | 2022-07-30 | 0 | 9 | 59 |  |  |  | 0 | 0 | 0 | 0.02274% | 0.8077% | 0.3822% | 0.4095% | 0.4036% | 0.3979% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-08-07 | 0.43% | 0.4479% | 0.43% | 0.4479% |  |  | 0.01791% | 2022-07-30 | 0 | 27 | 95 |  |  |  | 0 | 0 | 0 | 0.02957% | 0.8674% | 0.4969% | 0.5021% | 0.454% | 0.4545% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-08-14 | 0.4906% | 0.532% | 0.4906% | 0.532% |  |  | 0.04138% | 2022-07-30 | 0 | 35 | 85 |  |  |  | 0 | 0 | 0 | 0.04321% | 2.017% | 0.6676% | 0.6705% | 0.508% | 0.5092% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-08-21 | 0.5082% | 0.7754% | 0.5082% | 0.7754% |  |  | 0.2672% | 2022-07-30 | 0 | 35 | 85 |  |  |  | 0 | 0 | 0 | 0.06672% | 2.195% | 0.8002% | 3.413% | 0.5152% | 0.5246% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-08-28 | 0.5512% | 0.8529% | 0.5512% | 0.8529% |  |  | 0.3017% | 2022-07-30 | 0 | 35 | 72 |  |  |  | 0 | 0 | 0 | 0.09363% | 3.349% | 1.24% | 3.828% | 0.5224% | 0.5477% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-09-04 | 0.6083% | 0.9069% | 0.6083% | 0.9069% |  |  | 0.2987% | 2022-07-30 | 0 | 35 | 87 |  |  |  | 0 | 0 | 0 | 0.1183% | 4.845% | 1.85% | 3.873% | 0.5296% | 0.5709% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-09-11 | 0.6492% | 0.9661% | 0.6492% | 0.9661% |  |  | 0.3169% | 2022-07-30 | 0 | 18 | 71 |  |  |  | 0 | 0 | 0 | 0.1308% | 6.599% | 2.268% | 4.123% | 0.5368% | 0.5742% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-09-18 | 0.6909% | 1.023% | 0.6909% | 1.023% |  |  | 0.3322% | 2022-07-30 | 0 | 0 | 71 |  |  |  | 0 | 0 | 0 | 0.2259% | 8.832% | 2.712% | 4.21% | 0.5404% | 0.5792% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-09-25 | 0.7293% | 1.096% | 0.7293% | 1.096% |  |  | 0.3663% | 2022-07-30 | 0 | 0 | 68 |  |  |  | 0 | 0 | 0 | 0.3466% | 10.76% | 3.147% | 4.448% | 0.5404% | 0.5951% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-10-02 | 0.7686% | 1.142% | 0.7686% | 1.142% |  |  | 0.3731% | 2022-07-30 | 0 | 6 | 65 |  |  |  | 0 | 0 | 0 | 0.5068% | 12.24% | 3.583% | 4.541% | 0.5404% | 0.6047% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-10-09 | 0.8254% | 1.248% | 0.8254% | 1.248% |  |  | 0.4227% | 2022-07-30 | 0 | 16 | 111 |  |  |  | 0 | 0 | 0 | 0.7433% | 12.62% | 4.185% | 5.17% | 0.5431% | 0.6593% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-10-16 | 0.9387% | 1.362% | 0.9387% | 1.362% |  |  | 0.4229% | 2022-07-30 | 0 | 22 | 107 |  |  |  | 0 | 0 | 0 | 1.037% | 14.62% | 5.416% | 5.853% | 0.5496% | 0.6784% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-10-23 | 1.028% | 1.52% | 1.028% | 1.52% |  |  | 0.4918% | 2022-07-30 | 0 | 12 | 119 |  |  |  | 0 | 0 | 0 | 2.014% | 17.1% | 6.173% | 6.892% | 0.5577% | 0.704% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-10-30 | 1.144% | 1.647% | 1.144% | 1.647% |  |  | 0.5026% | 2022-07-30 | 0 | 12 | 165 |  |  |  | 0 | 0 | 0 | 3.07% | 19.68% | 7.282% | 7.402% | 0.5612% | 0.7417% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-11-06 | 1.281% | 1.87% | 1.281% | 1.87% |  |  | 0.589% | 2022-07-30 | 0 | 2 | 180 |  | 160047 | 160047 | 3 | 2 | 1 | 4.863% | 21.69% | 8.459% | 8.666% | 0.5648% | 0.8328% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-11-13 | 1.469% | 2.12% | 1.469% | 2.12% |  |  | 0.651% | 2022-07-30 | 0 | 0 | 171 |  | 178596 | 178596 | 5 | 3 | 2 | 7.177% | 24.01% | 10.16% | 10.62% | 0.5654% | 0.8818% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-11-20 | 1.692% | 2.387% | 1.692% | 2.387% |  |  | 0.6953% | 2022-08-02 | -3 | 0 | 169 |  | 197622 | 197622 | 7 | 4 | 3 | 10.27% | 26.11% | 12.1% | 12.96% | 0.5654% | 0.9179% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696
PJ3 | 2020-11-27 | 1.867% | 2.609% | 1.867% | 2.609% |  |  | 0.742% | 2022-08-02 | -3 | 0 | 194 |  | 216936 | 216936 | 7 | 6 | 1 | 13.94% | 28.86% | 13.31% | 14.49% | 0.5654% | 0.9637% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 64408580.5676 | 51499046.988 | 51499046.988 | 12909533.5796 | 455402696
PJ3 | 2020-12-04 | 2.062% | 2.735% | 2.062% | 2.735% |  |  | 0.673% | 2022-08-05 | -6 | 0 | 212 |  | 237231 | 237231 | 9 | 6 | 3 | 18.21% | 30.54% | 14.62% | 15.14% | 0.5654% | 1.009% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 64408580.5676 | 51499046.988 | 53423052.2165 | 12909533.5796 | 455402696
PJ3 | 2020-12-11 | 2.266% | 2.96% | 2.266% | 2.96% |  |  | 0.694% | 2022-08-05 | -6 | 0 | 214 |  | 257877 | 257877 | 16 | 10 | 6 | 22.68% | 34.01% | 15.99% | 16.12% | 0.5654% | 1.094% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 64408580.5676 | 51499046.988 | 53423052.2165 | 12909533.5796 | 455402696
PJ3 | 2020-12-18 | 2.492% | 3.241% | 2.492% | 3.241% |  |  | 0.7492% | 2022-08-10 | -11 | 6 | 259 |  | 276750 | 276750 | 17 | 10 | 7 | 26.5% | 36.9% | 17.78% | 18.02% | 0.5654% | 1.171% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 64408580.5676 | 53423052.2165 | 53423052.2165 | 10985528.3511 | 455402696
PJ3 | 2020-12-25 | 2.727% | 3.583% | 2.727% | 3.583% |  |  | 0.8558% | 2022-08-10 | -11 | 16 | 263 |  | 302346 | 302346 | 17 | 10 | 7 | 29.51% | 41.4% | 19.86% | 19.89% | 0.5681% | 1.283% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 64408580.5676 | 53423052.2165 | 53423052.2165 | 10985528.3511 | 455402696
PJ3 | 2021-01-01 | 3.037% | 3.963% | 3.037% | 3.963% |  |  | 0.9256% | 2022-08-17 | -18 | 24 | 260 |  | 328626 | 328626 | 18 | 11 | 7 | 31.52% | 42.82% | 23.05% | 23.07% | 0.5746% | 1.386% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 64408580.5676 | 53423052.2165 | 53423052.2165 | 10985528.3511 | 455402696
PJ3 | 2021-01-08 | 3.173% | 4.216% | 3.173% | 4.216% |  |  | 1.043% | 2022-08-17 | -18 | 24 | 254 |  | 355752 | 355752 | 18 | 11 | 7 | 33.05% | 45.92% | 24.23% | 24.25% | 0.5836% | 1.495% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 64408580.5676 | 53423052.2165 | 53423052.2165 | 10985528.3511 | 455402696
PJ3 | 2021-01-15 | 3.298% | 4.548% | 3.298% | 4.548% |  |  | 1.249% | 2022-08-20 | -21 | 36 | 277 |  | 382374 | 382374 | 18 | 17 | 1 | 33.94% | 48.53% | 25.43% | 25.44% | 0.5925% | 1.705% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 |  |  |  |  | 0 | 455402696
PJ3 | 2021-01-22 | 3.436% | 4.85% | 3.436% | 4.85% |  |  | 1.414% | 2022-08-24 | -25 | 19 | 279 |  | 409050 | 409050 | 18 | 17 | 1 | 34.62% | 51.74% | 26.8% | 26.81% | 0.605% | 1.84% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 76118626.0173 | 55432074.3659 | 55432074.3659 | 20686551.6514 | 455402696
PJ3 | 2021-01-29 | 3.59% | 5.16% | 3.59% | 5.16% |  |  | 1.57% | 2022-08-27 | -28 | 15 | 280 |  | 436752 | 436752 | 18 | 17 | 1 | 35.34% | 55.92% | 28.26% | 28.27% | 0.6269% | 1.97% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 76118626.0173 | 55432074.3659 | 57537699.8423 | 20686551.6514 | 455402696
PJ3 | 2021-02-05 | 3.739% | 5.47% | 3.739% | 5.47% |  |  | 1.731% | 2022-09-03 | -35 | 18 | 289 |  | 464130 | 464130 | 20 | 17 | 3 | 36.03% | 58.25% | 29.64% | 29.53% | 0.6507% | 2.15% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 76118626.0173 | 55432074.3659 | 57537699.8423 | 20686551.6514 | 455402696
PJ3 | 2021-02-12 | 3.882% | 5.76% | 3.882% | 5.76% |  |  | 1.878% | 2022-09-08 | -40 | 16 | 304 |  | 487359 | 487359 | 20 | 17 | 3 | 36.8% | 59.54% | 30.79% | 30.38% | 0.6882% | 2.38% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 82663530.9827 | 55432074.3659 | 57537699.8423 | 27231456.6168 | 455402696
PJ3 | 2021-02-19 | 4.106% | 6.05% | 4.106% | 6.05% |  |  | 1.944% | 2022-09-14 | -46 | 20 | 325 |  | 516681 | 516681 | 24 | 17 | 7 | 38.09% | 61.38% | 32.7% | 31.13% | 0.7353% | 2.59% | 0% | 0% |  |  |  | Open |  |  |  | Open |  |  |  | Open | [16 empty] | 455402696 | 0 | 82663530.9827 | 55432074.3659 | 57537699.8423 | 27231456.6168 | 455402696
PJ3 | 2021-02-26 | 4.287% | 6.28% | 4.287% | 6.28% |  |  | 1.993% | 2022-09-17 | -49 | 26 | 329 |  | 551628 | 551628 | 26 | 17 | 9 | 39.6% | 63.34% | 33.96% | 32.18% | 0.7895% | 2.73% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | [16 empty] | 455402696 | 0 | 82663530.9827 | 57537699.8423 | 57537699.8423 | 25125831.1404 | 455402696
PJ3 | 2021-03-05 | 4.482% | 6.54% | 4.482% | 6.54% |  |  | 2.058% | 2022-09-22 | -54 | 24 | 378 |  | 586646 | 586646 | 29 | 20 | 9 | 41.08% | 64.22% | 35.32% | 33.9% | 0.8509% | 2.84% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 23 | 14 | 2 | 2 |  | 0 | 0 | 0 | 0 |  |  | 8 | 4 | 4 | 1 |  | 455402696 | 0 | 82663530.9827 | 57537699.8423 | 59859836.38 | 25125831.1404 | 455402696
PJ3 | 2021-03-12 | 4.684% | 6.87% | 4.684% | 6.87% |  |  | 2.186% | 2022-09-15 | -47 | 24 | 466 |  | 624611 | 624611 | 31 | 22 | 9 | 42.69% | 65.05% | 36.71% | 35.91% | 0.9147% | 3.02% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 24 | 14 | 2 | 2 |  | 0 | 0 | 0 | 0 |  |  | 8 | 4 | 4 | 1 |  | 455402696 | -5417615.3 | 85230468.4691 | 57537699.8423 | 59859836.38 | 27692768.6268 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-03-19 | 4.893% | 7.41% | 4.893% | 7.41% |  |  | 2.517% | 2022-08-30 | -31 | 24 | 497 |  | 666189 | 666189 | 32 | 22 | 10 | 44.48% | 66.45% | 38.11% | 39.65% | 0.9806% | 3.25% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 27 | 10 | 10 | 1 |  | 0 | 0 | 0 | 0 |  |  | 8 | 4 | 4 | 1 |  | 455402696 | -5417615.3 | 85230468.4691 | 57537699.8423 | 59859836.38 | 27692768.6268 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-03-26 | 5.148% | 8.16% | 5.148% | 8.16% |  |  | 3.012% | 2022-09-03 | -35 | 91 | 508 |  | 711888 | 711888 | 32 | 24 | 8 | 46.73% | 67.63% | 39.88% | 42.73% | 1.054% | 3.8% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 22 | 10 | 11 | 2 |  | 0 | 0 | 0 | 0 |  |  | 8 | 5 | 5 | 0 |  | 455402696 | -5417615.3 | 85230468.4691 | 57537699.8423 | 59859836.38 | 27692768.6268 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-04-02 | 5.552% | 8.77% | 5.552% | 8.77% |  |  | 3.218% | 2022-09-07 | -39 | 104 | 483 |  | 758271 | 758271 | 34 | 24 | 10 | 49.32% | 68.38% | 42.96% | 45.38% | 1.168% | 4.25% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 22 | 15 | 12 | 2 |  | 0 | 0 | 0 | 0 |  |  | 8 | 5 | 5 | 0 |  | 455402696 | -5417615.3 | 85230468.4691 | 57537699.8423 | 59859836.38 | 27692768.6268 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-04-09 | 6.024% | 9.46% | 6.024% | 9.46% |  |  | 3.436% | 2022-09-13 | -45 | 111 | 471 |  | 803440 | 803440 | 35 | 25 | 10 | 52.68% | 68.93% | 46.07% | 48.39% | 1.338% | 4.75% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 22 | 15 | 12 | 2 |  | 0 | 0 | 0 | 0 |  |  | 8 | 6 | 5 | 0 |  | 455402696 | -5417615.3 | 85230468.4691 | 59859836.3772 | 62209627.2517 | 25370632.0919 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-04-16 | 6.408% | 10.08% | 6.408% | 10.08% |  |  | 3.672% | 2022-09-16 | -48 | 138 | 478 |  | 831847 | 831847 | 35 | 27 | 8 | 56.4% | 69.42% | 47.97% | 51.61% | 1.517% | 5.14% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 22 | 15 | 13 | 1 |  | 0 | 0 | 0 | 0 |  |  | 8 | 7 | 5 | 0 |  | 455402696 | -5417615.3 | 85230468.4691 | 59859836.3772 | 62209627.2517 | 25370632.0919 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-04-23 | 6.831% | 10.77% | 6.831% | 10.77% |  |  | 3.939% | 2022-09-17 | -49 | 155 | 504 |  | 859561 | 859561 | 35 | 29 | 6 | 60.57% | 70.57% | 49.56% | 54.64% | 1.758% | 5.63% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 26 | 15 | 13 | 1 |  | 0 | 0 | 0 | 0 |  |  | 8 | 7 | 5 | 0 |  | 455402696 | -5417615.3 | 88767253.3828 | 62209627.2517 | 62209627.2517 | 26557626.1311 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-04-30 | 7.32% | 11.44% | 7.32% | 11.44% |  |  | 4.12% | 2022-09-20 | -52 | 163 | 531 |  | 888265 | 888265 | 35 | 30 | 5 | 65.18% | 71.63% | 51.26% | 57.68% | 2.056% | 6.1% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 26 | 15 | 12 | 1 |  | 0 | 0 | 0 | 0 |  |  | 8 | 7 | 5 | 0 |  | 455402696 | -5417615.3 | 88767253.3828 | 62209627.2517 | 62209627.2517 | 26557626.1311 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-05-07 | 7.871% | 12.08% | 7.871% | 12.08% |  |  | 4.209% | 2022-09-25 | -57 | 134 | 523 |  | 917527 | 917527 | 38 | 33 | 5 | 70.24% | 73% | 52.94% | 59.78% | 2.417% | 6.61% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 28 | 18 | 12 | 2 |  | 0 | 0 | 0 | 0 |  |  | 8 | 7 | 5 | 0 |  | 455402696 | -5417615.3 | 88767253.3828 | 62209627.2517 | 62209627.2517 | 26557626.1311 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-05-14 | 8.316% | 12.64% | 8.316% | 12.64% |  |  | 4.324% | 2022-10-01 | -63 | 121 | 616 |  | 942961 | 942961 | 38 | 33 | 5 | 74.13% | 74.8% | 54.22% | 61.36% | 2.721% | 7.07% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 28 | 18 | 12 | 2 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 455402696 | -5417615.3 | 91559865.5482 | 62209627.2517 | 65518334.9222 | 29350238.2965 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-05-21 | 8.742% | 13.31% | 8.742% | 13.31% |  |  | 4.568% | 2022-10-03 | -65 | 188 | 619 |  | 1062445 | 1062445 | 39 | 35 | 4 | 77.66% | 76.91% | 55.33% | 62.63% | 3.028% | 7.69% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 28 | 19 | 13 | 2 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 455402696 | -5417615.3 | 91559865.5482 | 62209627.2517 | 65518334.9222 | 29350238.2965 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-05-28 | 9.572% | 14.22% | 9.572% | 14.22% |  |  | 4.648% | 2022-10-08 | -70 | 179 | 627 |  | 1112256 | 1112256 | 41 | 35 | 6 | 82.24% | 80.23% | 56.8% | 63.97% | 3.748% | 8.53% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 30 | 21 | 14 | 2 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 455402696 | -5417615.3 | 91559865.5482 | 62209627.2517 | 65518334.9222 | 29350238.2965 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-06-04 | 10.53% | 15.44% | 10.53% | 15.44% |  |  | 4.91% | 2022-10-13 | -75 | 184 | 625 |  | 1162442 | 1162442 | 41 | 35 | 6 | 85.86% | 81.37% | 59.21% | 65.55% | 4.548% | 9.78% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 30 | 24 | 17 | 2 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 0 |  | 455402696 | -5417615.3 | 91559865.5482 | 62209627.2517 | 65518334.9222 | 29350238.2965 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-06-11 | 11.66% | 16.61% | 11.66% | 16.61% |  |  | 4.954% | 2022-10-20 | -82 | 190 | 659 |  | 1220413 | 1220413 | 43 | 35 | 8 | 88.56% | 83.17% | 63.19% | 66.97% | 5.416% | 10.97% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 30 | 26 | 18 | 3 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 455402696 | -5417615.3 | 96104946.9053 | 65518334.9222 | 68133078.9448 | 30586611.9831 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-06-18 | 12.75% | 17.76% | 12.75% | 17.76% |  |  | 5.005% | 2022-10-25 | -87 | 172 | 661 |  | 1269995 | 1269995 | 44 | 38 | 6 | 90.69% | 86.97% | 66.65% | 68.15% | 6.316% | 12.11% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 32 | 26 | 18 | 3 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 455402696 | -5417615.3 | 96104946.9053 | 65518334.9222 | 68133078.9448 | 30586611.9831 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-06-25 | 13.83% | 18.9% | 13.83% | 18.9% |  |  | 5.066% | 2022-10-29 | -91 | 199 | 661 |  | 1323920 | 1323920 | 48 | 40 | 8 | 92.31% | 88.55% | 70.08% | 70.19% | 7.207% | 13.2% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 34 | 26 | 16 | 5 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 455402696 | -5417615.3 | 96104946.9053 | 68133078.9448 | 68133078.9448 | 27971867.9605 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-07-02 | 14.7% | 20.06% | 14.7% | 20.06% |  |  | 5.36% | 2022-11-03 | -96 | 279 | 670 |  | 1375711 | 1375711 | 50 | 41 | 9 | 93.39% | 88.99% | 73.55% | 73.09% | 8.09% | 14.27% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 34 | 28 | 16 | 6 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 455402696 | -5417615.3 | 96104946.9053 | 68133078.9448 | 68133078.9448 | 27971867.9605 | 449985080.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-07-09 | 15.92% | 21.41% | 15.92% | 21.41% |  |  | 5.49% | 2022-11-12 | -105 | 335 |  |  | 1431559 | 1431559 | 50 | 41 | 9 | 94.18% | 90.38% | 77.02% | 76.61% | 9.225% | 15.48% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 35 | 29 | 16 | 7 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14455620.7 | 96104946.9053 | 68133078.9448 | 68133078.9448 | 27971867.9605 | 469858316.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-07-16 | 17.36% | 22.59% | 17.36% | 22.59% |  |  | 5.23% | 2022-11-19 | -112 | 220 | 662 |  | 1488901 | 1488901 | 50 | 41 | 9 | 94.84% | 91.79% | 80.47% | 80.01% | 10.58% | 16.49% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. |  | Open | [5 empty] | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14455620.7 | 104403312.1199 | 72433092.2081 | 72433092.2081 | 31970219.9118 | 469858316.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-07-23 | 18.5% | 23.43% | 18.5% | 23.43% |  |  | 4.93% | 2022-11-22 | -115 | 480 | 642 |  | 1527606 | 1527606 | 50 | 41 | 9 | 95.09% | 92.39% | 82.16% | 82.52% | 11.46% | 17.22% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 34 | 29 | 15 | 7 |  | 0 | 0 | 0 | 0 |  |  | 9 | 8 | 7 | 9 |  | 455402696 |  |  |  |  | 0 | 455402696 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-07-30 | 20.28% | 24.89% | 20.28% | 24.89% |  |  | 4.61% | 2022-12-05 | -128 | 532 | 638 |  | 1595217 | 1595217 | 50 | 43 | 7 | 95.55% | 92.67% | 85.51% | 84% | 13.64% | 18.78% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 34 | 29 | 15 | 7 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14455620.7 | 87789580.2724 | 72433092.1981 | 79491215.0578 | 15356488.0743 | 469858316.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-08-06 | 22.41% | 26.71% | 22.41% | 26.71% |  |  | 4.3% | 2022-12-12 | -135 | 510 | 730 |  | 1656078 | 1656078 | 51 | 45 | 6 | 95.93% | 93.02% | 88.37% | 87.63% | 15.8% | 20.55% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 35 | 30 | 16 | 7 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14455620.7 | 87789580.2724 | 72433092.1981 | 79491215.0578 | 15356488.0743 | 469858316.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-08-13 | 24.39% | 28.45% | 24.39% | 28.45% |  |  | 4.06% | 2022-12-20 | -143 | 596 | 733 |  | 1717931 | 1717931 | 53 | 45 | 8 | 96.22% | 93.24% | 89.83% | 89.25% | 17.97% | 22.42% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 35 | 30 | 16 | 7 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14455620.7 | 88715090.5196 | 72433092.1981 | 79491215.0578 | 16281998.3215 | 469858316.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-08-20 | 26.55% | 30.25% | 26.55% | 30.25% |  |  | 3.7% | 2022-12-03 | -126 | 536 | 809 |  | 1784155 | 1784155 | 53 | 39 | 14 | 96.47% | 93.62% | 91.24% | 90.37% | 20.42% | 24.4% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 38 | 31 | 17 | 7 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14455620.7 | 88715090.5196 | 72433092.1981 | 79491215.0578 | 16281998.3215 | 469858316.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-08-27 | 28.91% | 32.04% | 28.91% | 32.04% |  |  | 3.13% | 2022-12-06 | -129 | 482 | 804 |  | 1850470 | 1850470 | 53 | 45 | 8 | 96.67% | 93.81% | 92.54% | 90.93% | 22.59% | 26.44% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 39 | 34 | 18 | 7 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14455620.7 | 88715090.5196 | 72433092.1981 | 79491215.0578 | 16281998.3215 | 469858316.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-09-03 | 30.83% | 33.8% | 30.83% | 33.8% |  |  | 2.974% | 2022-12-13 | -136 | 556 | 893 |  | 1930003 | 1930003 | 53 | 46 | 7 | 96.84% | 93.96% | 93.76% | 91.7% | 24.68% | 28.42% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 40 | 35 | 19 | 8 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14455620.7 | 88715090.5196 | 79491215.0578 | 88020345.3006 | 9223875.4619 | 469858316.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-09-10 | 33.03% | 36.03% | 33.03% | 36.03% |  |  | 3% | 2022-12-19 | -142 | 522 | 1120 |  | 1998267 | 1998267 | 53 | 46 | 7 | 97% | 94.1% | 94.87% | 92.44% | 27.18% | 30.61% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 40 | 35 | 19 | 8 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14455620.7 | 104186483.02 | 88020345.3006 | 88020345.3006 | 16166137.7194 | 469858316.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-09-17 | 35.22% | 37.93% | 35.22% | 37.93% |  |  | 2.71% | 2023-01-18 | -172 | 513 | 1171 |  | 1970954 | 1970954 | 55 | 46 | 9 | 97.14% | 94.18% | 95.92% | 92.61% | 29.68% | 32.76% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 42 | 35 | 17 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14455620.7 | 104186483.02 | 88020345.3006 | 88020345.3006 | 16166137.7194 | 469858316.7 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-09-24 | 37.81% | 40.27% | 37.81% | 40.27% |  |  | 2.46% | 2023-01-23 | -177 | 547 | 1168 |  | 2060742 | 2060742 | 56 | 46 | 10 | 97.22% | 94.23% | 96.8% | 92.81% | 32.63% | 35.46% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 44 | 35 | 17 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 455402696 | 14875883.16 | 104186483.02 | 88020345.3006 | 88020345.3006 | 16166137.7194 | 470278579.16 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-10-01 | 40.57% | 42.35% | 40.57% | 42.35% |  |  | 1.78% | 2023-01-28 | -182 | 550 | 1179 |  | 2151873 | 2151873 | 57 | 50 | 7 | 97.27% | 94.3% | 97.58% | 93.04% | 35.82% | 37.81% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 44 | 35 | 16 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 8 | 9 |  | 455402696 | 14875883.16 | 104186483.02 | 88020345.3006 | 88020345.3006 | 16166137.7194 | 470278579.16 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-10-08 | 43.34% | 44.5% | 43.34% | 44.5% |  |  | 1.16% | 2023-01-28 | -182 | 543 | 1173 |  | 2144928 | 2144928 | 57 | 51 | 6 | 97.33% | 94.36% | 98.26% | 93.23% | 38.9% | 40.24% | 0.6029% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 38 | 18 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 8 | 9 |  | 455402696 | 14633790.59 | 104186483.02 | 88020345.3006 | 103022245.8431 | 16166137.7194 | 470036486.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-10-15 | 46.18% | 46.98% | 46.18% | 46.98% |  |  | 0.8% | 2023-01-31 | -185 | 606 | 1175 |  | 2229222 | 2229222 | 59 | 51 | 8 | 97.38% | 94.44% | 98.94% | 93.44% | 42.19% | 43.04% | 1.206% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 42 | 22 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 455402696 | 14633790.59 | 125286661.4148 | 88020345.3006 | 103022245.8431 | 37266316.1142 | 470036486.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-10-22 | 49.39% | 49.43% | 49.39% | 49.43% |  |  | 0.04% | 2023-02-06 | -191 | 590 | 1172 |  | 2312992 | 2312992 | 59 | 51 | 8 | 97.43% | 94.45% | 99.52% | 93.56% | 45.88% | 45.87% | 1.809% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 42 | 22 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 455402696 | 14633790.59 | 125286661.4148 | 103022245.8431 | 103022245.8431 | 22264415.5717 | 470036486.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-10-29 | 52.68% | 51.87% | 52.68% | 51.87% |  |  | -0.81% | 2023-02-13 | -198 | 579 | 1172 |  | 2373532 | 2373532 | 59 | 51 | 8 | 97.49% | 94.54% | 99.67% | 93.7% | 49.7% | 48.66% | 2.412% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 43 | 23 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 455402696 | 14633790.59 | 125286661.4148 | 103022245.8431 | 103022245.8431 | 22264415.5717 | 470036486.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-11-05 | 56.04% | 54.23% | 56.04% | 54.23% |  |  | -1.81% | 2023-02-21 | -206 | 513 | 1163 |  | 2424004 | 2424004 | 59 | 51 | 8 | 97.54% | 94.6% | 99.81% | 93.83% | 53.55% | 51.41% | 3.001% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 43 | 23 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 455402696 | 14633790.59 | 124022894.8432 | 103022245.8431 | 124022894.8432 | 21000649.0001 | 470036486.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-11-12 | 59.59% | 56.51% | 59.59% | 56.51% |  |  | -3.08% | 2023-03-06 | -219 | 496 | 952 |  | 2776762 | 2776762 | 59 | 54 | 5 | 97.6% | 94.59% | 99.94% | 93.97% | 57.71% | 54% | 3.564% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 44 | 20 | 12 |  | 1 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 455402696 | 14633790.59 | 139354321.4886 | 103022245.8431 | 124022894.8432 | 36332075.6454 | 470036486.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-11-19 | 63.25% | 58.23% | 63.25% | 58.23% |  |  | -5.02% | 2023-03-15 | -228 | 375 | 906 |  | 2856163 | 2856163 | 62 | 54 | 8 | 97.65% | 94.63% | 100% | 94.03% | 61.98% | 56% | 4.127% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 44 | 20 | 12 |  | 1 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 455402696 | 14633790.59 | 139354321.4886 | 124022894.8432 | 124022894.8432 | 15331426.6454 | 470036486.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-11-26 | 66.9% | 59.92% | 66.9% | 59.92% |  |  | -6.98% | 2023-03-18 | -231 | 343 | 981 |  | 2922918 | 2922918 | 62 | 56 | 6 | 97.7% | 94.65% | 100% | 94.11% | 66.23% | 57.97% | 4.69% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 44 | 18 | 15 |  | 1 | 0 | 0 | 0 |  |  | 9 | 8 | 6 | 8 |  | 455402696 | 14633790.59 | 139354321.4886 | 124022894.8432 | 124022894.8432 | 15331426.6454 | 470036486.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-12-03 | 70.44% | 61.33% | 70.44% | 61.33% |  |  | -9.11% | 2023-03-21 | -234 | 336 | 1050 |  | 2999715 | 2999715 | 65 | 57 | 8 | 97.76% | 94.68% | 100% | 94.19% | 70.4% | 59.6% | 5.253% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 44 | 18 | 15 |  | 1 | 0 | 0 | 0 |  |  | 9 | 8 | 6 | 8 |  | 455402696 | 14633790.59 | 136807901.0821 | 124022894.8432 | 136807901.0821 | 12785006.2389 | 470036486.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-12-10 | 73.71% | 62.68% | 73.71% | 62.68% |  |  | -11.03% | 2023-03-21 | -234 | 338 | 1004 |  | 3085954 | 3085954 | 65 | 57 | 8 | 97.8% | 94.7% | 100% | 94.24% | 74.14% | 61.18% | 6.133% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 44 | 18 | 15 |  | 1 | 0 | 0 | 0 |  |  | 9 | 8 | 6 | 8 |  | 455402696 | 14633790.59 | 136807901.0821 | 124022894.8432 | 136807901.0821 | 12785006.2389 | 470036486.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-12-17 | 76.64% | 63.95% | 76.64% | 63.95% |  |  | -12.69% | 2023-03-21 | -234 | 276 | 967 |  | 3163148 | 3163148 | 65 | 59 | 6 | 97.8% | 94.73% | 100% | 94.36% | 77.54% | 62.66% | 8.211% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 44 | 18 | 15 |  | 1 | 0 | 0 | 0 |  |  | 9 | 8 | 6 | 8 |  | 455402696 | 14581626.59 | 136807901.0821 | 124022894.8432 | 136807901.0821 | 12785006.2389 | 469984322.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-12-24 | 78.44% | 64.88% | 78.44% | 64.88% |  |  | -13.56% | 2023-03-23 | -236 | 283 | 913 |  | 3250818 | 3250818 | 66 | 59 | 7 | 97.8% | 94.75% | 100% | 94.39% | 79.59% | 63.73% | 9.943% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 46 | 44 | 18 | 15 |  | 1 | 0 | 0 | 0 |  |  | 9 | 8 | 6 | 8 |  | 455402696 | 14581626.59 | 136807901.0821 | 124022894.8432 | 136807901.0821 | 12785006.2389 | 469984322.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2021-12-31 | 80.45% | 65.62% | 80.45% | 65.62% |  |  | -14.83% | 2023-03-22 | -235 | 264 | 913 |  |  |  | 66 | 60 | 6 | 97.8% | 94.82% | 100% | 94.41% | 81.94% | 64.59% | 12.02% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | [5 empty] | 2 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 455402696 | 14581626.59 | 151372789 | 136807901 | 151372789 | 14564888 | 469984322.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-01-07 | 82.34% | 66.63% | 82.34% | 66.63% |  |  | -15.71% | 2023-03-22 | -235 | 230 | 910 |  |  |  | 66 | 60 | 6 | 97.8% | 94.83% | 100% | 94.46% | 84.09% | 65.77% | 14.1% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | [5 empty] | 2 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 455402696 |  |  |  |  | 0 | 455402696 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-01-14 | 84.14% | 67.66% | 84.14% | 67.66% |  |  | -16.48% | 2023-03-25 | -238 | 197 | 872 |  | 3483111 | 3483111 | 66 | 60 | 6 | 97.8% | 94.85% | 100% | 94.52% | 86.21% | 66.97% | 15.62% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 51 | 15 | 6 | 15 |  | 2 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 455402696 |  |  |  |  | 0 | 455402696 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-01-21 | 85.87% | 68.61% | 85.87% | 68.61% |  |  | -17.26% | 2023-04-02 | -246 | 185 | 832 |  | 3554869 | 3554869 | 66 | 60 | 6 | 97.8% | 94.9% | 100% | 94.54% | 88.23% | 68.08% | 16.11% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 52 | 15 | 6 | 15 |  | 2 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 455402696 | 14581626.59 | 167197889.1537 | 151372789.8241 | 151372789 | 15825099.3296 | 469984322.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-01-28 | 87.55% | 69.59% | 87.55% | 69.59% |  |  | -17.96% | 2023-04-08 | -252 | 152 | 795 |  | 3623657 | 3623657 | 66 | 61 | 5 | 97.8% | 94.92% | 100% | 94.61% | 90.19% | 69.21% | 16.6% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 52 | 15 | 6 | 15 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 455402696 | 14581626.59 | 167197889.1537 | 151372789.8241 | 151372789 | 15825099.3296 | 469984322.59 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-02-04 | 88.67% | 70.39% | 88.67% | 70.39% |  |  | -18.28% | 2023-04-16 | -260 | 127 | 786 |  | 3700056 | 3700056 | 66 | 63 | 3 | 97.8% | 94.93% | 100% | 94.64% | 91.48% | 70.16% | 17.08% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 53 | 47 | 6 | 15 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 455402696 | -6929796.51 | 215801543.4601 | 151372789.8241 | 165731909.6626 | 64428753.636 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-02-11 | 89.61% | 71.05% | 89.61% | 71.05% |  |  | -18.56% | 2023-04-27 | -271 | 149 | 907 |  | 3756036 | 3756036 | 66 | 63 | 3 | 97.8% | 94.96% | 100% | 94.68% | 92.58% | 70.91% | 17.41% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 53 | 47 | 6 | 15 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 455402696 | -6929796.51 | 215801543.4601 | 151372789.8241 | 165731909.6626 | 64428753.636 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-02-18 | 90.77% | 72.02% | 90.77% | 72.02% |  |  | -18.75% | 2023-05-04 | -278 | 165 | 911 |  | 3828960 | 3828960 | 67 | 63 | 4 | 97.8% | 94.98% | 100% | 94.72% | 93.94% | 72.04% | 17.79% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 53 | 47 | 6 | 15 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 455402696 | -6929796.51 | 215801543.4601 | 215789596.8601 | 215789596.8601 | 11946.6 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-02-25 | 92% | 73.03% | 92% | 73.03% |  |  | -18.97% | 2023-05-11 | -285 | 168 | 912 |  | 3904267 | 3904267 | 67 | 64 | 3 | 97.8% | 95.06% | 100% | 94.75% | 95.38% | 73.22% | 18.86% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 56 | 50 | 10 | 15 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 455402696 | -6929796.51 | 215801543.4601 | 215789596.8601 | 215789596.8601 | 11946.6 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-03-04 | 93.14% | 74.06% | 93.14% | 74.06% |  |  | -19.08% | 2023-05-20 | -294 | 105 | 910 |  | 3979451 | 3979451 | 69 | 64 | 5 | 97.84% | 95.1% | 100% | 94.8% | 96.69% | 74.42% | 20.5% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 56 | 50 | 10 | 15 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 455402696 | -6929796.51 | 215801543.4601 | 215789596.8601 | 215789596.8601 | 11946.6 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-03-11 | 93.93% | 74.98% | 93.93% | 74.98% |  |  | -18.95% | 2023-05-24 | -298 | 100 | 913 |  | 4054585 | 4054585 | 71 | 64 | 7 | 97.92% | 95.14% | 100% | 94.87% | 97.54% | 75.49% | 24.73% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 55 | 51 | 10 | 15 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 455402696 | -6929796.51 | 264438505.8459 | 215789596.8601 | 215789596.8601 | 48648908.9858 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-03-18 | 94.55% | 75.84% | 94.55% | 75.84% |  |  | -18.71% | 2023-05-30 | -304 | 96 | 916 |  | 4129924 | 4129924 | 74 | 64 | 10 | 98% | 95.17% | 100% | 95.08% | 98.2% | 76.48% | 28.97% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 55 | 51 | 10 | 15 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 455402696 | -6929796.51 | 264438505.8459 | 253191243.7942 | 253191243.7942 | 11247262.0517 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-03-25 | 95.15% | 76.68% | 95.15% | 76.68% |  |  | -18.47% | 2023-06-10 | -315 | 73 | 916 |  | 4205729 | 4205729 | 74 | 65 | 9 | 98.08% | 95.27% | 100% | 95.23% | 98.73% | 77.43% | 32.81% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 55 | 52 | 10 | 15 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 455402696 | -6929796.51 | 264438505.8459 | 253191243.7942 | 253191243.7942 | 11247262.0517 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-04-01 | 95.72% | 77.46% | 95.72% | 77.46% |  |  | -18.26% | 2023-06-10 | -315 | 51 | 915 |  | 4281946 | 4281946 | 74 | 66 | 8 | 98.16% | 95.4% | 100% | 95.34% | 99.19% | 78.33% | 36.48% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 55 | 52 | 10 | 15 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 455402696 | -6929796.51 | 283518151.116 | 253191243.7942 | 253191243.7942 | 30326907.3218 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-04-08 | 96.18% | 78.02% | 96.18% | 78.02% |  |  | -18.16% | 2023-06-15 | -320 | 55 | 917 |  | 4328944 | 4328944 | 74 | 66 | 8 | 98.25% | 95.46% | 100% | 95.5% | 99.5% | 78.97% | 45.08% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 55 | 52 | 10 | 15 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 455402696 | -6929796.51 | 283518151.116 | 253191243.7942 | 253191243.7942 | 30326907.3218 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-04-15 | 96.55% | 78.63% | 96.55% | 78.63% |  |  | -17.92% | 2023-06-20 | -325 | 76 | 918 |  | 4376248 | 4376248 | 74 | 67 | 7 | 98.41% | 95.49% | 100% | 95.85% | 99.71% | 79.65% | 52.27% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 56 | 53 | 7 | 17 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 455402696 | -6929796.51 | 283518151.116 | 253191243.7942 | 281950763.3842 | 30326907.3218 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-04-22 | 96.9% | 79.25% | 96.9% | 79.25% |  |  | -17.65% | 2023-06-13 | -318 | 79 | 910 |  | 4423708 | 4423708 | 74 | 67 | 7 | 98.59% | 95.53% | 100% | 95.97% | 99.86% | 80.36% | 60.43% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 56 | 53 | 7 | 17 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 455402696 | -6929796.51 | 283518151.116 | 281950763.3842 | 281950763.3842 | 1567387.7318 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-04-29 | 97.2% | 79.69% | 97.2% | 79.69% |  |  | -17.51% | 2023-06-14 | -319 | 35 | 890 |  | 4471042 | 4471042 | 74 | 67 | 7 | 98.81% | 95.55% | 100% | 96% | 99.96% | 80.87% | 69.76% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 56 | 53 | 7 | 17 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 455402696 | -6929796.51 | 283518151.116 | 281950763.3842 | 281950763.3842 | 1567387.7318 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-05-06 | 97.3% | 79.9% | 97.3% | 79.9% |  |  | -17.4% | 2023-06-11 | -316 | 96 | 936 |  | 4499012 | 4499012 | 75 | 68 | 7 | 98.9% | 95.57% | 100% | 96.1% | 99.97% | 81.11% | 73.81% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 56 | 53 | 7 | 17 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 455402696 | -6929796.51 | 301964519.5532 | 281950763.3842 | 281950763.3842 | 20013756.169 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-05-13 | 97.6% | 80.28% | 97.6% | 80.28% |  |  | -17.32% | 2023-06-17 | -322 | 89 | 926 |  | 4574164 | 4574164 | 80 | 68 | 12 | 99.15% | 95.6% | 100% | 96.23% | 100% | 81.54% | 86.02% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 56 | 53 | 10 | 17 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 455402696 | -6929796.51 | 301964519.5532 | 281950763.3842 | 281950763.3842 | 20013756.169 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-05-20 | 97.79% | 80.48% | 97.79% | 80.48% |  |  | -17.31% | 2023-06-21 | -326 | 82 | 914 |  | 4648468 | 4648468 | 80 | 69 | 11 | 99.4% | 95.71% | 100% | 96.33% | 100% | 81.76% | 90.7% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 56 | 53 | 10 | 17 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 455402696 | -6929796.51 | 301964519.5532 | 281950763.3842 | 301964519.5532 | 20013756.169 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-05-27 | 97.99% | 80.69% | 97.99% | 80.69% |  |  | -17.3% | 2023-06-28 | -333 | 77 | 905 |  | 4721611 | 4721611 | 81 | 70 | 11 | 99.62% | 95.73% | 100% | 96.5% | 100% | 82% | 95.27% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 55 | 52 | 7 | 17 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 455402696 | -6929796.51 | 301964519.5532 | 281950763.3842 | 301964519.5532 | 20013756.169 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-06-03 | 98.27% | 80.92% | 98.27% | 80.92% |  |  | -17.35% | 2023-07-04 | -339 | 64 | 887 |  | 4782166 | 4782166 | 82 | 70 | 12 | 99.79% | 95.78% | 100% | 96.59% | 100% | 82.25% | 97.68% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 55 | 53 | 8 | 17 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 455402696 | -6929796.51 | 301964519.5532 | 281950763.3842 | 301964519.5532 | 20013756.169 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-06-10 | 98.53% | 81.12% | 98.53% | 81.12% |  |  | -17.41% | 2023-07-08 | -343 | 57 | 876 |  | 4853455 | 4853455 | 82 | 71 | 11 | 99.88% | 95.83% | 100% | 96.63% | 100% | 82.48% | 98.82% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 55 | 53 | 8 | 17 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 455402696 | -6929796.51 | 301964519.5532 | 281950763.3842 | 301964519.5532 | 20013756.169 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-06-17 | 98.79% | 81.3% | 98.79% | 81.3% |  |  | -17.49% | 2023-05-04 | 0 | 48 | 889 |  | 4924368 | 4924368 | 82 | 73 | 9 | 99.94% | 99.84% | 100% | 96.7% | 100% | 82.69% | 99.43% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 62 | 55 |  | 28 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 455402696 | -6929796.51 | 307040049.2464 | 281950763.3842 | 301964519.5532 | 25089285.8622 | 448472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-06-24 | 99.05% | 81.51% | 99.05% | 81.51% |  |  | -17.54% | 2023-05-04 | 0 | 44 | 898 |  | 4995993 | 4995993 | 82 | 75 | 7 | 99.99% | 95.87% | 100% | 96.79% | 100% | 82.92% | 99.78% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 64 | 56 |  | 42 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 307040049.2464 | 281950763.3842 | 301964519.5532 | 25089285.8622 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-07-01 | 99.31% | 81.7% | 99.31% | 81.7% |  |  | -17.61% | 2023-05-04 | 0 | 23 |  |  | 5056578 | 5056578 | 83 | 76 | 7 | 100% | 95.89% | 100% | 96.84% | 100% | 83.14% | 99.95% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 64 | 56 |  | 42 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 362987063.2722 | 361993394.6722 | 362987063.2722 | 993668.6 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-07-08 | 99.55% | 81.86% | 99.55% | 81.86% |  |  | -17.69% | 2023-05-04 | 0 | 7 | 823 |  | 5132215 | 5132215 | 83 | 77 | 6 | 100% |  | 100% |  | 100% | 83.32% | 100% |  | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | [5 empty] | 4 | 0 | 0 | 4 |  |  | 13 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 387987063.2722 | 386993394.6722 | 387987063.2722 | 993668.6 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-07-15 | 99.67% | 82.01% | 99.67% | 82.01% |  |  | -17.66% | 2023-05-04 | 0 | 32 | 958 |  | 5194330 | 5194330 | 83 | 77 | 6 | 100% | 95.92% | 100% | 96.93% | 100% | 83.49% | 100% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 67 | 56 |  | 53 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 387987063.2722 | 386993394.6722 | 387987063.2722 | 993668.6 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-07-22 | 99.85% | 82.17% | 78.12% | 78.18% |  |  | 0.05925% | 2023-05-04 | 0 | 49 | 957 |  | 5276437 | 5276437 | 85 | 77 | 8 | 100% | 95.94% | 100% | 96.97% | 100% | 83.67% | 100% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 72 | 56 |  | 53 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 387987063.2722 | 386993394.6722 | 387987063.2722 | 993668.6 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-07-29 | 99.98% | 82.33% | 79.31% | 79.83% |  |  | 0.5247% | 2023-05-04 | 0 | 11 | 957 |  | 5358075 | 5358075 | 85 | 78 | 7 | 100% | 96.02% | 100% | 96.98% | 100% | 83.85% | 100% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 72 | 58 |  | 53 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 397987063.3122 | 395987063.2922 | 397987063.3122 | 2000000.02 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-08-05 | 100% | 83.34% | 80.45% | 80.91% |  |  | 0.4628% | 2023-05-04 | 0 | 617 | 974 |  | 5438808 | 5438808 | 87 | 79 | 8 | 100% | 96.3% | 100% | 97.56% | 100% | 84.97% | 100% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 72 | 58 |  | 53 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 397987063.3122 | 395987063.2922 | 397987063.3122 | 2000000.02 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-08-12 | 100% | 84.05% | 81.47% | 81.87% |  |  | 0.4013% | 2023-05-04 | 0 | 603 | 1006 |  | 5518625 | 5518625 | 87 | 79 | 8 | 100% | 96.37% | 100% | 97.83% | 100% | 85.78% | 100% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 72 | 58 |  | 53 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 413736267.0822 | 395987063.2922 | 413736267.0822 | 17749203.79 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-08-19 | 100% | 84.7% | 82.44% | 82.8% |  |  | 0.3613% | 2023-05-04 | 0 | 570 | 1017 |  | 5599762 | 5599762 | 87 | 79 | 8 | 100% | 96.45% | 100% | 98.09% | 100% | 86.51% | 100% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 73 | 58 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 413736267.0822 | 413736267.0822 | 413736267.0822 | 0 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-08-25 | 100% |  | 83.43% | 83.75% |  |  | 0.322% | 2023-04-25 | 9 | 499 | 1021 |  | 5682453 | 5682453 | 89 | 81 | 8 | 97.63% | 96.47% | 97.12% | 98.76% | 84.18% | 86.29% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 73 | 58 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 426862444.0722 | 413736267.0822 | 413736267.0822 | 13126176.99 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-09-01 | 100% |  | 84.45% | 84.65% |  |  | 0.2012% | 2023-04-27 | 7 | 528 | 1033 |  | 5810318 | 5810318 | 91 | 81 | 10 | 97.94% | 96.52% | 97.35% | 99.08% | 85.62% | 87.11% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 73 | 58 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 426862444.0722 | 413736267.0822 | 413736267.0822 | 13126176.99 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-09-08 | 100% |  | 85.66% | 85.57% |  |  | -0.08956% | 2023-05-01 | 3 | 539 | 1033 |  | 5895245 | 5895245 | 93 | 81 | 12 | 98.16% | 96.61% | 97.44% | 99.18% | 87.05% | 87.95% | 0% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 73 | 58 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 442727197.3522 | 442727197.3522 | 442727197.3522 | 0 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-09-15 | 100% |  | 87.24% | 86.52% |  |  | -0.72% | 2023-05-03 | 1 | 704 | 1086 |  | 5993782 | 5993782 | 95 | 81 | 14 | 98.7% | 96.76% | 97.47% | 99.26% | 87.82% | 88.77% | 0.79% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 73 | 65 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 442727197.3522 | 442727197.3522 | 442727197.3522 | 0 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-09-22 | 100% |  | 88.77% | 87.45% |  |  | -1.317% | 2023-05-06 | -2 | 704 | 1112 |  | 6080912 | 6080912 | 96 | 83 | 13 | 98.83% | 97.25% | 97.73% | 99.31% | 89.39% | 89.66% | 1.99% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 73 | 65 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 454295564.1522 | 444226254.3922 | 446226254.4322 | 10069309.76 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-09-29 | 100% |  | 89.89% | 88.26% |  |  | -1.635% | 2023-05-11 | -7 | 553 | 1168 |  | 6180253 | 6180253 | 96 | 83 | 13 | 98.93% | 97.36% | 97.95% | 99.36% | 90.86% | 90.59% | 3.18% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 73 | 65 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 455804268.2922 | 452815852.6722 | 455304268.2722 | 2988415.62 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-10-06 | 100% |  | 90.69% | 89.02% |  |  | -1.671% | 2023-05-13 | -9 | 244 | 1190 |  | 6275483 | 6275483 | 97 | 84 | 13 | 99% | 97.47% | 98.11% | 99.38% | 91.96% | 91.34% | 4.38% | 0% | COVID-19: Risk of disruption of Design/Procurement & Construction in case any of the stakeholders is affected. | All stakeholder to follow Government guidelines. Contractor to anticipate delays and plan to overcome any such delays. | ALL | Open | Delay in Procurement | Procurement Strategy finalized. Contractor to update status monthly. | Follow up to be done on the agreed strategy | Open | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | 74 | 65 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 459145278.9722 | 456417138.6522 | 459008278.9522 | 2728140.32 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-10-13 |  |  | 91.31% | 89.62% |  |  | -1.69% | 2023-05-15 | -11 | 136 | 1190 |  | 6372773 | 6372773 | 97 | 88 | 9 | 99.05% | 97.58% | 98.24% | 99.41% | 92.85% | 92.02% | 6.95% | 0% | Delayed site handover: Risk of other Contractors delaying site handover to this Contractor | Close coordination is required between all stakeholders. Client should put due pressure on other Contractors to release the areas as per this Contract conditions. | ALL | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open |  |  |  | Open | 76 | 65 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 466241351.8622 | 456417138.6522 | 459008278.9522 | 9824213.21 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-10-20 |  |  | 91.81% | 89.93% |  |  | -1.883% | 2023-05-21 | -17 | 142 | 1146 |  | 6470663 | 6470663 | 97 | 89 | 8 | 99.09% | 97.61% | 98.36% | 99.48% | 93.47% | 92.53% | 12.8% | 0% | Obstructions by other Contractors along Internal roads North | Coordination ongoing between all stakeholders to ensure release of obstructed areas. Client should put due pressure on other Contractors to remove the obstructions. | ALL | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open |  |  |  | Open | 76 | 65 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 466241351.8622 | 449008278.9322 | 464651084.8122 | 17233072.93 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-10-27 |  |  | 92.24% | 90.12% |  |  | -2.124% | 2023-05-28 | -24 | 151 | 1044 |  | 6623980 | 6623980 | 97 | 89 | 8 | 99.13% | 97.68% | 98.48% | 99.51% | 93.9% | 92.8% | 18.86% | 0% | Obstructions by other Contractors along Internal roads North | Coordination ongoing between all stakeholders to ensure release of obstructed areas. Client should put due pressure on other Contractors to remove the obstructions. | ALL | Open |  |  |  | Open |  |  |  | Open | 76 | 65 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 470109263.6822 | 465698956.3322 | 469131575.6622 | 4410307.35 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-11-03 |  |  | 92.99% | 90.25% |  |  | -2.739% | 2023-06-04 | -31 | 160 | 994 |  | 6669629 | 6669629 | 97 | 91 | 6 | 98.97% | 97.72% | 98.6% | 99.53% | 94.52% | 93% | 24.92% | 0% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the current situation of lead time. Contractor to update status monthly. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 76 | 65 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 470109263.6822 | 455698956.3122 | 469131575.6622 | 14410307.37 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-11-10 |  |  | 93.79% | 90.34% |  |  | -3.447% | 2023-06-11 | -38 | 463 | 903 |  | 6756722 | 6756722 | 99 | 91 | 8 | 99.21% | 97.74% | 98.71% | 99.54% | 94.98% | 93.11% | 30.8% | 0% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the current situation of lead time. Contractor to update status monthly. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 76 | 65 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 483043954.1222 | 468558077.4022 | 483043954.1222 | 14485876.72 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-11-17 |  |  | 94.5% | 90.34% |  |  | -4.164% | 2023-06-18 | -45 | 446 | 230 |  | 6832965 | 6832965 | 99 | 91 | 8 | 99.28% | 97.76% | 98.83% | 99.54% | 95.76% | 93.22% | 36.46% | 0% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the current situation of lead time. Contractor to update status monthly. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 76 | 65 |  | 54 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 483043954.1222 | 468558077.4022 | 483043954.1222 | 14485876.72 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-11-24 |  |  | 95.39% | 90.34% |  |  | -5.046% | 2023-06-25 | -52 | 245 | 236 |  | 6856721 | 6856721 | 99 | 91 | 8 | 99.17% | 97.81% | 98.94% | 99.54% | 96.57% | 93.22% | 39.57% | 0% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the current situation of lead time. Contractor to update status monthly. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 77 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 483043954.1222 | 468558077.4022 | 483043954.1222 | 14485876.72 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-12-01 |  |  | 96.21% | 90.34% |  |  | -5.866% | 2023-07-04 | -61 | 229 | 236 |  | 6887639 | 6887639 | 99 | 91 | 8 | 99.41% | 97.83% | 99.05% | 99.54% | 97.44% | 93.22% | 42.67% | 0% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the current situation of lead time. Contractor to update status monthly. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 77 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 484175697.0722 | 473305654.9922 | 483555687.0322 | 10870042.08 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-12-08 |  |  | 96.7% | 90.34% |  |  | -6.362% | 2023-07-11 | -68 | 229 | 236 |  | 6911822 | 6911822 | 99 | 91 | 8 | 99.41% | 97.84% | 99.17% | 99.55% | 98.45% | 93.22% | 45.78% | 0% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the current situation of lead time. Contractor to update status monthly. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 77 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 484175697.0722 | 473305654.9922 | 483555687.0322 | 10870042.08 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-12-15 |  |  | 96.93% | 90.4% |  |  | -6.533% | 2023-07-18 | -75 | 130 | 348 |  | 6936049 | 6936049 | 101 | 91 | 10 | 99.54% | 97.85% | 99.28% | 99.55% | 98.96% | 93.22% | 48.38% | 0% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the current situation of lead time. Contractor to update status monthly. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 77 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 484175697.0722 | 473305654.9922 | 483555687.0322 | 10870042.08 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-12-22 |  |  | 97.15% | 90.48% |  |  | -6.67% | 2023-07-24 | -81 | 68 | 361 |  | 6961642 | 6961642 | 101 | 91 | 10 | 99.54% | 97.85% | 99.37% | 99.56% | 99.22% | 93.25% | 48.38% | 3.21% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the current situation of lead time. Contractor to update status monthly. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 77 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 484379446.0922 | 473305654.9922 | 483555687.0322 | 11073791.1 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2022-12-29 |  |  | 97.33% | 90.54% |  |  | -6.791% | 2023-07-29 | -86 | 87 | 364 |  | 6996734 | 6996734 | 101 | 91 | 10 | 99.54% | 97.85% | 99.49% | 99.58% | 99.4% | 93.29% | 48.38% | 7.32% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the current situation of lead time. Contractor to update status monthly. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 78 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 484379446.0922 | 473305654.9922 | 483555687.0322 | 11073791.1 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-01-05 |  |  | 97.46% | 90.62% |  |  | -6.837% | 2023-08-03 | -91 | 87 | 418 |  | 7038058 | 7038058 | 101 | 91 | 10 | 99.73% | 97.88% | 99.6% | 99.58% | 99.52% | 93.31% | 48.39% | 10.99% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the current situation of lead time. Contractor to update status monthly. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 78 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 488769786.0822 | 474417302.0922 | 484486031.1322 | 14352483.99 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-01-12 |  |  | 97.59% | 90.69% |  |  | -6.9% | 2023-08-10 | -98 | 62 | 415 |  | 7074516 | 7074516 | 101 | 91 | 10 | 99.8% | 97.89% | 99.71% | 99.59% | 99.63% | 93.33% | 48.39% | 12.01% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 78 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 488769786.0822 | 474417302.0922 | 484486031.1322 | 14352483.99 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-01-19 |  |  | 97.76% | 90.78% |  |  | -6.976% | 2023-08-17 | -105 | 56 | 415 |  | 7111001 | 7111001 | 103 | 91 | 12 | 99.87% | 98.06% | 99.83% | 99.64% | 99.72% | 93.35% | 48.4% | 12.01% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 78 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 488769786.0822 | 474417302.0922 | 484486031.1322 | 14352483.99 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-01-26 |  |  | 97.99% | 90.88% |  |  | -7.106% | 2023-08-23 | -111 | 55 | 415 |  | 7147485 | 7147485 | 104 | 91 | 13 | 99.93% | 98.06% | 99.94% | 99.69% | 99.79% | 93.38% | 48.4% | 12.2% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 78 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 488769786.0822 | 474417302.0922 | 484486031.1322 | 14352483.99 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-02-02 |  |  | 98.17% | 90.95% |  |  | -7.219% | 2023-08-30 | -118 | 49 | 411 |  | 7190485 | 7190485 | 106 | 91 | 15 | 99.96% | 98.07% | 100% | 99.73% | 99.85% | 93.42% | 48.4% | 12.31% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 78 | 65 |  | 55 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 455402696 | 33070203.49 | 488769786.0822 | 474417302.0922 | 484486031.1322 | 14352483.99 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-02-09 |  |  | 98.32% | 91.01% |  |  | -7.312% | 2023-09-06 | -125 | 55 | 408 |  | 7226757 | 7226757 | 108 | 91 | 17 | 99.96% | 98.15% | 100% | 99.74% | 99.9% | 93.44% | 48.81% | 13.73% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 78 | 65 |  | 55 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 487486031.2522 | 474417302.0922 | 484486031.1322 | 13068729.16 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-02-16 |  |  | 98.51% | 91.07% |  |  | -7.444% | 2023-09-12 | -131 | 70 | 321 |  | 7256739 | 7256739 | 108 | 91 | 17 | 99.97% | 98.19% | 100% | 99.75% | 99.92% | 93.49% | 48.81% | 13.73% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 487486031.2522 | 474417302.0922 | 484486031.1322 | 13068729.16 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-02-23 |  |  | 98.68% | 91.15% |  |  | -7.534% | 2023-09-19 | -138 | 98 | 313 |  | 7286550 | 7286550 | 108 | 91 | 17 | 99.98% | 98.22% | 100% | 99.75% | 99.96% | 93.53% | 66.18% | 16.13% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 487486031.2522 | 474417302.0922 | 484486031.1322 | 13068729.16 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-03-02 |  |  | 98.92% | 91.23% |  |  | -7.686% | 2023-09-24 | -143 | 141 | 313 |  | 7320431 | 7320431 | 108 | 91 | 17 | 99.98% | 98.24% | 100% | 99.75% | 99.98% | 93.58% | 77.05% | 18.32% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 487486031.2522 | 474417302.0922 | 484486031.1322 | 13068729.16 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-03-09 |  |  | 98.92% | 91.31% |  |  | -7.606% | 2023-09-30 | -149 | 170 | 296 |  | 7347814 | 7347814 | 109 | 91 | 18 | 99.99% | 98.26% | 100% | 99.75% | 99.99% | 93.64% | 88.07% | 19.09% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 487486031.2522 | 474417302.0922 | 484486031.1322 | 13068729.16 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-03-16 |  |  | 99.27% | 91.38% |  |  | -7.891% | 2023-10-01 | -150 | 170 | 296 |  | 7374767 | 7374767 | 109 | 93 | 16 | 100% | 98.27% | 100% | 99.76% | 99.99% | 93.69% | 98.36% | 19.79% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 487486031.2522 | 474417302.0922 | 484486031.1322 | 13068729.16 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-03-23 |  |  | 99.39% | 91.44% |  |  | -7.951% | 2023-10-07 | -156 | 152 | 263 |  | 7399348 | 7399348 | 110 | 93 | 17 | 100% | 98.29% | 100% | 99.78% | 99.99% | 93.72% | 98.36% | 20.66% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 487486031.2522 | 474417302.0922 | 484486031.1322 | 13068729.16 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-03-30 |  |  | 99.5% | 91.5% |  |  | -8.004% | 2023-10-12 | -161 | 116 | 291 |  | 7418429 | 7418429 | 111 | 93 | 18 | 100% | 98.29% | 100% | 99.78% | 99.99% | 93.75% | 99.9% | 21.28% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 487486031.2522 | 474417302.0922 | 484486031.1322 | 13068729.16 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-04-06 |  |  | 99.62% | 91.55% |  |  | -8.068% | 2023-10-18 | -167 | 53 | 291 |  | 7434479 | 7434479 | 113 | 93 | 20 | 100% | 98.29% | 100% | 99.78% | 100% | 93.77% | 99.9% | 22.65% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 487486031.2522 | 474417302.0922 | 484486031.1322 | 13068729.16 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-04-13 |  |  | 99.75% | 91.59% |  |  | -8.162% | 2023-10-25 | -174 | 31 | 291 |  | 7450391 | 7450391 | 113 | 94 | 19 | 100% | 98.3% | 100% | 99.78% | 100% | 93.8% | 100% | 23.35% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486323033.4622 | 474417302.0922 | 486323033.4622 | 11905731.37 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-04-20 |  |  | 99.87% | 91.62% |  |  | -8.252% | 2023-11-01 | -181 | 23 | 291 |  | 7465139 | 7465139 | 116 | 94 | 22 | 100% | 98.32% | 100% | 99.78% | 100% | 93.81% | 100% | 24.02% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486323033.4622 | 474417302.0922 | 486323033.4622 | 11905731.37 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-04-27 |  |  | 100% | 91.68% |  |  | -8.32% | 2023-11-05 | -185 | 43 | 291 |  | 7477013 | 7477013 | 116 | 94 | 22 | 100% | 98.32% | 100% | 99.78% | 100% | 93.81% | 100% | 24.55% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486323033.4622 | 474417302.0922 | 486323033.4622 | 11905731.37 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-05-04 |  |  | 100% | 91.7% |  |  | -8.3% | 2023-11-12 | -192 | 74 | 291 |  | 7500645 | 7500645 | 116 | 94 | 22 | 100% | 98.32% | 100% | 99.78% | 100% | 93.82% | 100% | 25.6% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486323033.4622 | 474417302.0922 | 486323033.4622 | 11905731.37 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-05-11 |  |  | 100% | 91.73% |  |  | -8.27% | 2023-11-19 | -199 | 0 | 291 |  | 7528948 | 7528948 | 116 | 102 | 14 | 100% | 98.32% | 100% | 99.78% | 100% | 93.82% | 100% | 26.13% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486323033.4622 | 474417302.0922 | 486323033.4622 | 11905731.37 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-05-18 |  |  | 100% | 91.75% |  |  | -8.25% | 2023-11-26 | -206 | 0 | 291 |  | 7553687 | 7553687 | 116 | 102 | 14 | 100% | 98.32% | 100% | 99.78% | 100% | 93.83% | 100% | 26.52% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486488223.3099 | 474417302.0922 | 486323033.4622 | 12070921.2177 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-05-25 |  |  | 100% | 91.76% |  |  | -8.24% | 2023-12-03 | -213 | 0 | 201 |  | 7605960 | 7605960 | 116 | 102 | 14 | 100% | 98.32% | 100% | 99.78% | 100% | 93.85% | 100% | 26.52% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486488223.3099 | 474417302.0922 | 486323033.4622 | 12070921.2177 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-06-01 |  |  | 100% | 91.81% |  |  | -8.19% | 2023-12-09 | -219 | 0 | 272 |  | 7609717 | 7609717 | 118 | 105 | 13 | 100% | 98.32% | 100% | 99.78% | 100% | 93.87% | 100% | 26.52% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486488223.3099 | 474417302.0922 | 486323033.4622 | 12070921.2177 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-06-08 |  |  | 100% | 91.87% |  |  | -8.13% | 2023-12-16 | -226 | 0 | 270 |  | 7632686 | 7632686 | 119 | 105 | 14 | 100% | 98.32% | 100% | 99.78% | 100% | 93.92% | 100% | 26.8% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486488223.3099 | 474417302.0922 | 486323033.4622 | 12070921.2177 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-06-15 |  |  | 100% | 91.93% |  |  | -8.07% | 2023-12-24 | -234 | 0 | 270 |  | 7655519 | 7655519 | 119 | 106 | 13 | 100% | 98.32% | 100% | 99.78% | 100% | 94% | 100% | 27.01% | Delay in Procurement | Contractor to ensure all materials are finalized and delivered at site considering the without impacting the SA1 - Completion date. | Contractor | Open | Contractor’s delay in procurement of remaining trees. Contract Potential risk of Time impact to the Completion date | Direct payment to Sub-Contractor initiated to expedite the delivery. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Follow-up being done with the Contractor. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486488223.3099 | 474417302.0922 | 486323033.4622 | 12070921.2177 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-06-22 |  |  | 100% | 91.96% |  |  | -8.04% | 2023-12-31 | -241 | 0 | 243 |  | 7677759 | 7677759 | 120 | 106 | 14 | 100% | 98.32% | 100% | 99.78% | 100% | 94.06% | 100% | 27.32% | Contractor’s delay in procurement of remaining trees. Potential risk of Time impact to the Overall Completion date | Contractor failed in providing a forecast to deliver all remining trees. Delay letters are being issued to the Contractor. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Workshops held with all stakeholders and code B obtained for the detail design. Contractor to endorse remaining comments and submit IFC. Contractor being requested to issue a schedule for hardscape snags completion in Road A4. | Contractor | Open | Concerns on the quality of executed works | Contractor to endorse NCRs/SORs issued by CSC. Contractor being requested to issue a schedule for hardscape snags completion in Road A4. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486488223.3099 | 474417302.0922 | 486323033.4622 | 12070921.2177 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-06-29 |  |  | 100% | 92.03% |  |  | -7.97% | 2024-01-06 | -247 | 0 | 261 |  | 7688073 | 7688073 | 120 | 106 | 14 | 100% | 98.33% | 100% | 99.78% | 100% | 94.08% | 100% | 27.57% | Contractor’s delay in procurement of remaining trees. Potential risk of Time impact to the Overall Completion date | Contractor failed in providing a forecast to deliver all remining trees. Delay letters are being issued to the Contractor. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Workshops held with all stakeholders and code B obtained for the detail design. Contractor to endorse remaining comments and submit IFC. Contractor being requested to issue a schedule for hardscape snags completion in Road A4. | Contractor | Open | Concerns on the quality of executed works | Contractor to endorse NCRs/SORs issued by CSC. Contractor being requested to issue a schedule for hardscape snags completion in Road A4. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486488223.3099 | 474417302.0922 | 486323033.4622 | 12070921.2177 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-07-06 |  |  | 100% | 92.07% |  |  | -7.93% | 2024-01-11 | -252 | 0 | 261 |  | 7715256 | 7715256 | 120 | 107 | 13 | 100% | 98.34% | 100% | 99.78% | 100% | 94.15% | 100% | 27.57% | Contractor’s delay in procurement of remaining trees. Potential risk of Time impact to the Overall Completion date | Contractor failed in providing a forecast to deliver all remining trees. Issue being addressed in progress meetings. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Workshops held with all stakeholders and code B obtained for the detail design. Contractor to endorse remaining comments and submit IFC. Contractor being requested to issue a schedule for hardscape snags completion in Road A4. | Contractor | Open | Concerns on the quality of executed works | Contractor to endorse NCRs/SORs issued by CSC. Contractor being requested to issue a schedule for hardscape snags completion in Road A4. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486488223.3099 | 474417302.0922 | 486323033.4622 | 12070921.2177 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-07-13 |  |  | 100% | 92.07% |  |  | -7.93% | 2024-01-18 | -259 | 0 | 261 |  | 7739506 | 7739506 | 120 | 107 | 13 | 100% | 98.34% | 100% | 99.78% | 100% | 94.19% | 100% | 27.73% | Contractor’s delay in procurement of remaining trees. Potential risk of Time impact to the Overall Completion date | Contractor failed in providing a forecast to deliver all remining trees. Issue being addressed in progress meetings. | Contractor | Open | Delays in D&B scope of works for the Smart City requirements | Workshops held with all stakeholders and code B obtained for the detail design. Contractor to endorse remaining comments and submit IFC. Contractor being requested to issue a schedule for hardscape snags completion in Road A4. | Contractor | Open | Concerns on the quality of executed works | Contractor to endorse NCRs/SORs issued by CSC. Contractor being requested to issue a schedule for hardscape snags completion in Road A4. | Contractor | Open | 79 | 75 | 1 | 54 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 455402696 | 33070203.49 | 486488223.3099 | 474417302.0922 | 486323033.4622 | 12070921.2177 | 488472899.49 | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-07-20 |  |  | 100% | [50 empty] | 455402696 | 33070203.49 | 486488223.3099 | 474417302.0922 | 486323033.4622 |  |  | Delays in Ancillary structural works impacting Completion date (Overall Completion) | Delays in procurement of stone cladding, elevators, escalators etc for Ancillary impacting Completion date (Overall Completion) | Delays in completion of electrical shop drawings for Ancillary impacting Completion date (Overall Completion)
PJ3 | 2023-07-27 |  |  | 100%
PJ3 | 2023-08-03 |  |  | 100%
PJ3 | 2023-08-10 |  |  | 100%
PJ3 | 2023-08-17 |  |  | 100%
PJ3 | 2023-08-24 |  |  | 100%
PJ3 | 2023-08-31 |  |  | 100%
PJ3 | 2023-09-07 |  |  | 100%
PJ3 | 2023-09-14 |  |  | 100%
PJ3 | 2023-09-21 |  |  | 100%
PJ3 | 2023-09-28 |  |  | 100%
PJ3 | 2023-10-05 |  |  | 100%
PJ3 | 2023-10-12 |  |  | 100%
Formulas:
Date = +[Date, row above]+7

## PJ1
Project ID | Date | Original Plan% | Original Act % | Rev.1 Plan% | Rev.1 Act % | Rev.2 Plan% | Rev.2 Act % | Variance % (Act-Plan) | Forecast Completion | No. of days delayed | Planned Manpower | Actual Manpower | Mandays | Total Manhours | Total Manhours after LTI | HSE NCR Issued to Date | HSE NCRs Closed | HSE NCRs Open | Engineering: Baseline : Planned % | Engineering: Actual % | Procurement : Baseline : Planned % | Procurement : Actual % | Construction works : Baseline : Planned % | Construction works : Actual % | Commissioning/ Snagging : Baseline : Planned % - | Commissioning/ Snagging : Actual % - | R1 - Risk Description | R1 - Risk Mitigation | R1 - Action by | R1 - Status | R2- Risk Description | R2- Risk Mitigation | R2- Action by | R2- Status | R3- Risk Description | R3- Risk Mitigation | R3- Action by | R3- Status | I1- Item | I1- Mitigation Action | I1- Item | I2- Description | I2- Mitigation Action | I2- Item | I3- Description | I3- Mitigation Action | I3- Item | I3- Description | I3- Mitigation Action | Change Requests Issued to Contractor | CR Provided Cost & Time Impacts by Contractor | CR Under Client Review | CR Agreed by both paries | CRNot accepted | Variation Issued to Contractor | Variation Provided Cost & Time Impacts by Contractor | Variation Under Client Review | Variation Agreed by both paries | Variation Not accepted | SI | Si Issued to Contractor | SI Provided Cost & Time Impacts by Contractor | SIUnder Client Review | SI Agreed by both paries | SI Not accepted | Project cost - Original | Variations approved | Net Total Invoice requested | Net Total Paid to date | Net Certified to date | Payment remaining | Estimate at completion | Top Driving Item 1 | Top Driving Item 2 | Top Driving Item 3
PJ1 | 2020-03-27 | 0% | 0.005176% | 0% | 0.005176% |  |  | 0.005176% | 2022-03-09 |  | 18 | 18 |  |  |  | 0 | 0 | 0
PJ1 | 2020-04-03 | 0% | 0.0159% | 0% | 0.0159% |  |  | 0.0159% | 2022-02-19 |  | 18 | 18 |  |  |  | 0 | 0 | 0
PJ1 | 2020-04-10 | 0.04636% | 0.08716% | 0.04636% | 0.08716% |  |  | 0.04079% | 2022-03-12 |  | 18 | 18 |  |  |  | 0 | 0 | 0
PJ1 | 2020-04-17 | 0.1863% | 0.2739% | 0.1863% | 0.2739% |  |  | 0.08765% | 2022-03-19 |  | 32 | 32 |  |  |  | 0 | 0 | 0
PJ1 | 2020-04-24 | 0.3304% | 0.4736% | 0.3304% | 0.4736% |  |  | 0.1432% | 2022-03-23 |  | 44 | 44 |  |  |  | 0 | 0 | 0
PJ1 | 2020-05-01 | 0.4571% | 0.6867% | 0.4571% | 0.6867% |  |  | 0.2297% | 2022-03-30 |  | 44 | 44 |  |  |  | 0 | 0 | 0
PJ1 | 2020-05-08 | 0.5863% | 0.8605% | 0.5863% | 0.8605% |  |  | 0.2741% | 2022-03-20 |  | 46 | 46 |  |  |  | 0 | 0 | 0
PJ1 | 2020-05-15 | 0.7199% | 1.01% | 0.7199% | 1.01% |  |  | 0.2905% | 2022-03-22 |  | 45 | 45 |  |  |  | 0 | 0 | 0
PJ1 | 2020-05-22 | 0.7897% | 1.064% | 0.7897% | 1.064% |  |  | 0.2743% | 2022-03-24 |  | 45 | 45 |  |  |  | 0 | 0 | 0
PJ1 | 2020-05-29 | 0.8192% | 1.091% | 0.8192% | 1.091% |  |  | 0.2717% | 2022-03-20 |  | 45 | 45 |  |  |  | 0 | 0 | 0
PJ1 | 2020-06-05 | 0.8932% | 1.18% | 0.8932% | 1.18% |  |  | 0.2866% | 2022-03-19 |  | 60 | 60 |  |  |  | 0 | 0 | 0
PJ1 | 2020-06-12 | 1.003% | 1.415% | 1.003% | 1.415% |  |  | 0.4123% | 2022-03-20 |  | 57 | 57 |  |  |  | 0 | 0 | 0
PJ1 | 2020-06-19 | 1.166% | 1.599% | 1.166% | 1.599% |  |  | 0.4326% | 2022-03-26 |  | 57 | 57 |  |  |  | 0 | 0 | 0
PJ1 | 2020-06-26 | 1.378% | 1.723% | 1.378% | 1.723% |  |  | 0.3456% | 2022-03-29 |  | 57 | 57 |  |  |  | 0 | 0 | 0
PJ1 | 2020-07-03 | 1.572% | 1.941% | 1.572% | 1.941% |  |  | 0.3687% | 2022-04-03 |  | 59 | 59 |  |  |  | 0 | 0 | 0
PJ1 | 2020-07-10 | 1.772% | 2.096% | 1.772% | 2.096% |  |  | 0.3239% | 2022-04-12 | -18 | 59 | 59 |  |  |  | 0 | 0 | 0
PJ1 | 2020-07-17 | 2.043% | 2.246% | 2.043% | 2.246% |  |  | 0.2034% | 2022-04-09 | 0 | 69.5 | 139 |  |  |  | 0 | 0 | 0
PJ1 | 2020-07-24 | 2.299% | 2.685% | 2.299% | 2.685% |  |  | 0.3868% | 2022-04-17 | -21 | 79.5 | 159 |  |  |  | 0 | 0 | 0
PJ1 | 2020-07-31 | 2.543% | 2.734% | 2.543% | 2.734% |  |  | 0.1913% | 2022-04-17 |  | 76 | 152 |  |  |  | 0 | 0 | 0
PJ1 | 2020-08-07 | 2.657% | 2.77% | 2.657% | 2.77% |  |  | 0.1126% | 2022-04-19 | -32 | 76 | 152 |  |  |  | 0 | 0 | 0
PJ1 | 2020-08-14 | 2.865% | 2.87% | 2.865% | 2.87% |  |  | 0.005102% | 2022-04-21 | -39 | 76.5 | 153 |  |  |  | 0 | 0 | 0
PJ1 | 2020-08-21 | 2.994% | 3.104% | 2.994% | 3.104% |  |  | 0.1098% | 2022-04-21 | -29 | 76 | 152 |  |  |  | 0 | 0 | 0
PJ1 | 2020-08-28 | 3.151% | 3.604% | 3.151% | 3.604% |  |  | 0.4533% | 2022-04-23 | -31 | 77.5 | 155 |  |  |  | 0 | 0 | 0
PJ1 | 2020-09-04 | 3.414% | 3.949% | 3.414% | 3.949% |  |  | 0.5349% | 2022-04-28 | -33 | 94 | 188 |  |  |  | 0 | 0 | 0
PJ1 | 2020-09-11 | 3.712% | 4.329% | 3.712% | 4.329% |  |  | 0.6175% | 2022-04-30 | -29 | 94.5 | 189 |  |  |  | 0 | 0 | 0
PJ1 | 2020-09-18 | 4.032% | 4.8% | 4.032% | 4.8% |  |  | 0.7674% | 2022-04-30 | -28 | 95 | 190 |  |  |  | 0 | 0 | 0
PJ1 | 2020-09-25 | 4.398% | 5.405% | 4.398% | 5.405% |  |  | 1.007% | 2022-04-30 | -29 | 99.5 | 199 |  |  |  | 0 | 0 | 0
PJ1 | 2020-10-02 | 4.793% | 6.04% | 4.793% | 6.04% |  |  | 1.246% | 2022-04-30 | -35 | 99.5 | 199 |  |  |  | 0 | 0 | 0
PJ1 | 2020-10-09 | 5.119% | 6.371% | 5.119% | 6.371% |  |  | 1.252% | 2022-05-07 | -38 | 104.5 | 209 |  |  |  | 0 | 0 | 0
PJ1 | 2020-10-16 | 5.421% | 6.844% | 5.421% | 6.844% |  |  | 1.423% | 2022-05-10 | -43 | 106 | 212 |  |  |  | 0 | 0 | 0
PJ1 | 2020-10-23 | 5.75% | 7.37% | 5.75% | 7.37% |  |  | 1.621% | 2022-05-16 | -52 | 127.5 | 255 |  |  |  | 0 | 0 | 0
PJ1 | 2020-10-30 | 6.082% | 8.713% | 6.082% | 8.713% |  |  | 2.632% | 2022-05-21 | -49 | 127.5 | 255 |  |  |  | 0 | 0 | 0
PJ1 | 2020-11-06 | 6.41% | 9.321% | 6.41% | 9.321% |  |  | 2.911% | 2022-05-26 | -57 | 127 | 254 |  |  |  | 0 | 0 | 0
PJ1 | 2020-11-13 | 6.746% | 10.27% | 6.746% | 10.27% |  |  | 3.528% | 2022-05-26 | -57 | 127 | 254 |  |  |  | 0 | 0 | 0
PJ1 | 2020-11-20 | 7.105% | 11.17% | 7.105% | 11.17% |  |  | 4.065% | 2022-05-31 | -59 | 151 | 302 |  |  |  | 0 | 0 | 0
PJ1 | 2020-11-27 | 7.477% | 11.81% | 7.477% | 11.81% |  |  | 4.337% | 2022-06-06 | -61 | 150.5 | 301 |  |  |  | 0 | 0 | 0
PJ1 | 2020-12-04 | 7.82% | 12.45% | 7.82% | 12.45% |  |  | 4.629% | 2022-06-11 | -61 | 150.5 | 301 |  |  |  | 0 | 0 | 0
PJ1 | 2020-12-11 | 8.176% | 13.2% | 8.176% | 13.2% |  |  | 5.026% | 2022-06-11 | -63 | 149.5 | 299 |  |  |  | 0 | 0 | 0
PJ1 | 2020-12-18 | 8.567% | 13.73% | 8.567% | 13.73% |  |  | 5.16% | 2022-06-14 | -68 | 149 | 298 |  |  |  | 0 | 0 | 0
PJ1 | 2020-12-25 | 8.937% | 14.44% | 8.937% | 14.44% |  |  | 5.507% | 2022-06-18 | -70 | 149 | 298 |  |  |  | 0 | 0 | 0
PJ1 | 2021-01-01 | 9.385% | 15.11% | 9.385% | 15.11% |  |  | 5.724% | 2022-06-19 | -70 | 149 | 298 |  |  |  | 0 | 0 | 0
PJ1 | 2021-01-08 | 9.901% | 15.72% | 9.901% | 15.72% |  |  | 5.821% | 2022-06-25 | -70 | 150.5 | 301 |  |  |  | 0 | 0 | 0
PJ1 | 2021-01-15 | 10.4% | 16.37% | 10.4% | 16.37% |  |  | 5.965% | 2022-06-29 | -70 | 150.5 | 301 |  |  |  | 0 | 0 | 0
PJ1 | 2021-01-22 | 10.91% | 16.93% | 10.91% | 16.93% |  |  | 6.017% | 2022-07-02 | -77 | 150.5 | 301 |  |  |  | 0 | 0 | 0
PJ1 | 2021-01-29 | 11.56% | 17.39% | 11.56% | 17.39% |  |  | 5.831% | 2022-07-07 | -80 | 150.5 | 301 |  |  |  | 0 | 0 | 0
PJ1 | 2021-02-05 | 12.2% | 18.12% | 12.2% | 18.12% |  |  | 5.92% | 2022-07-13 | -86 | 150.5 | 301 |  |  |  | 0 | 0 | 0
PJ1 | 2021-02-12 | 12.82% | 18.6% | 12.82% | 18.6% |  |  | 5.777% | 2022-07-19 | -91 | 149.5 | 299 |  |  |  | 0 | 0 | 0
PJ1 | 2021-02-19 | 13.56% | 19.21% | 13.56% | 19.21% |  |  | 5.645% | 2022-07-19 | -96 | 149.5 | 299 |  |  |  | 0 | 0 | 0
PJ1 | 2021-02-26 | 14.54% | 19.61% | 14.54% | 19.61% |  |  | 5.075% | 2022-07-26 | -96 | 153.5 | 307 |  |  |  | 0 | 0 | 0
PJ1 | 2021-03-05 | 16.04% | 19.93% | 16.04% | 19.93% |  |  | 3.888% | 2022-07-30 | -101 | 153.5 | 307 | 62507 | 557073 | 557073 | 20 | 19 | 1 | 78.85% | 60.71% | 82.84% | 78.36% | 8.89% | 14.27% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | [16 empty] | 224759024 | 0 | 33298909 | 31451721 | 31451721 | 1847188 | 224759024
PJ1 | 2021-03-12 | 17.78% | 20.34% | 17.78% | 20.34% |  |  | 2.563% | 2022-08-02 | -107 | 153.5 | 307 | 64643 | 576297 | 576297 | 20 | 19 | 1 | 80.94% | 61.82% | 84.37% | 80% | 10.7% | 14.56% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 12 | 9 | 4 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 4 | 4 | 1 |  | 224759024 | 0 | 33298909 | 31451721 | 31451721 | 1847188 | 224759024
PJ1 | 2021-03-19 | 19.45% | 20.76% | 19.45% | 20.76% |  |  | 1.314% | 2022-08-04 | -112 | 153.5 | 307 | 66779 | 595521 | 595521 | 20 | 19 | 1 | 82.74% | 61.93% | 85.88% | 80.97% | 12.45% | 14.95% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 12 | 9 | 4 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 4 | 4 | 1 |  | 224759024 | 0 | 33298909 | 31451721 | 31451721 | 1847188 | 224759024
PJ1 | 2021-03-26 | 21.07% | 21.63% | 21.07% | 21.63% |  |  | 0.5641% | 2022-08-09 | -112 | 153.5 | 307 | 68915 | 614745 | 614745 | 20 | 19 | 1 | 84.23% | 66.99% | 87.3% | 82.65% | 14.16% | 15.68% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 12 | 9 | 5 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 5 | 5 | 0 |  | 224759024 | 0 | 33298909 | 32899899 | 32899899 | 399010 | 224759024
PJ1 | 2021-04-02 | 22.62% | 22.4% | 22.62% | 22.4% |  |  | -0.2194% | 2022-08-16 | -115 | 153.5 | 307 | 71051 | 633969 | 633969 | 20 | 19 | 1 | 85.42% | 71.24% | 88.63% | 84.2% | 15.8% | 16.33% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 14 | 10 | 7 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 5 | 5 | 0 |  | 224759024 | 0 | 37749514 | 32899899 | 32899899 | 4849615 | 224759024
PJ1 | 2021-04-09 | 24.13% | 22.75% | 24.13% | 22.75% |  |  | -1.379% | 2022-08-17 | -119 | 170 | 340 | 73187 | 653193 | 653193 | 20 | 20 | 0 | 86.59% | 72.16% | 89.91% | 85.04% | 17.4% | 16.63% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 14 | 10 | 6 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 6 | 5 | 0 |  | 224759024 | 0 | 37749514 | 32899899 | 32899899 | 4849615 | 224759024
PJ1 | 2021-04-16 | 25.83% | 23.85% | 25.83% | 23.85% |  |  | -1.983% | 2022-08-17 | -120 | 170 | 340 | 75323 | 669213 | 669213 | 22 | 20 | 2 | 87.56% | 72.64% | 90.65% | 85.92% | 19.24% | 17.8% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 14 | 10 | 5 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 7 | 5 | 0 |  | 224759024 | 0 | 37749514 | 32899899 | 32899899 | 4849615 | 224759024
PJ1 | 2021-04-23 | 27.62% | 24.6% | 27.62% | 24.6% |  |  | -3.015% | 2022-08-30 | -126 | 165 | 330 | 77459 | 682029 | 682029 | 23 | 21 | 2 | 88.46% | 72.88% | 91.21% | 86.88% | 21.21% | 18.59% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 15 | 11 | 6 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 7 | 5 | 0 |  | 224759024 | 0 | 37749514 | 32899899 | 32899899 | 4849615 | 224759024
PJ1 | 2021-04-30 | 29.49% | 25.6% | 29.49% | 25.6% |  |  | -3.89% | 2022-09-06 | -130 | 201.5 | 403 | 79595 | 694845 | 694845 | 23 | 21 | 2 | 89.29% | 73.7% | 91.63% | 87.3% | 23.38% | 19.68% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 15 | 12 | 6 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 7 | 5 | 0 |  | 224759024 | 0 | 37749514 | 35851759 | 35851759 | 1897755 | 224759024
PJ1 | 2021-05-07 | 31.39% | 27.19% | 31.39% | 27.19% |  |  | -4.2% | 2022-09-10 | -133 | 222 | 444 | 82511 | 712341 | 712341 | 24 | 22 | 2 | 89.97% | 73.82% | 92.12% | 87.92% | 25.52% | 21.46% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 15 | 12 | 6 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 7 | 5 | 0 |  | 224759024 | 0 | 37749514 | 35851759 | 35851759 | 1897755 | 224759024
PJ1 | 2021-05-14 | 33.06% | 27.67% | 33.06% | 27.67% |  |  | -5.392% | 2022-09-13 | -138 | 243.5 | 487 | 85427 | 727017 | 727017 | 25 | 23 | 2 | 90.47% | 74.06% | 92.57% | 88.61% | 27.34% | 21.94% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 15 | 12 | 7 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 224759024 | 0 | 37749514 | 35851759 | 35851759 | 1897755 | 224759024
PJ1 | 2021-05-21 | 34.77% | 28.5% | 34.77% | 28.5% |  |  | -6.271% | 2022-09-28 | -144 | 248.5 | 497 | 89333 | 762171 | 762171 | 25 | 23 | 2 | 90.92% | 74.88% | 93.26% | 89.28% | 29.22% | 22.82% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 15 | 12 | 7 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 224759024 | 0 | 38224722.34 | 35851759 | 35851759 | 2372963.34 | 224759024
PJ1 | 2021-05-28 | 37.23% | 29.38% | 37.23% | 29.38% |  |  | -7.85% | 2022-10-04 | -150 | 248.5 | 497 | 93215 | 797109 | 797109 | 25 | 23 | 2 | 91.47% | 75.74% | 93.99% | 90.18% | 32.07% | 23.73% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 15 | 12 | 7 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 224759024 | 0 | 38224722.34 | 35851759 | 35851759 | 2372963.34 | 224759024
PJ1 | 2021-06-04 | 39.92% | 29.56% | 39.92% | 29.56% |  |  | -10.36% | 2022-10-11 | -150 | 248.5 | 497 | 97097 | 832047 | 832047 | 25 | 23 | 2 | 91.95% | 76.07% | 94.59% | 90.7% | 35.12% | 23.89% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 17 | 12 | 7 | 4 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 0 |  | 224759024 | 0 | 38224722.34 | 37910212.77 | 37910212.77 | 314509.57 | 224759024
PJ1 | 2021-06-11 | 42.65% | 29.74% | 42.65% | 29.74% |  |  | -12.91% | 2022-10-18 | -157 | 248.5 | 497 | 100979 | 866985 | 866985 | 25 | 23 | 2 | 92.28% | 76.59% | 95.08% | 91.05% | 38.22% | 24.05% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 17 | 14 | 9 | 5 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 224759024 | 0 | 38224722.34 | 37910212.77 | 37910212.77 | 314509.57 | 224759024
PJ1 | 2021-06-18 | 45.08% | 29.91% | 45.08% | 29.91% |  |  | -15.17% | 2022-11-02 | -161 | 248.5 | 497 | 104861 | 901923 | 901923 | 25 | 23 | 2 | 92.61% | 79.32% | 95.58% | 91.4% | 40.99% | 24.14% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 17 | 14 | 9 | 5 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 224759024 | 0 | 38224722.34 | 37910212.77 | 37910212.77 | 314509.57 | 224759024
PJ1 | 2021-06-25 | 47.44% | 30.16% | 47.44% | 30.16% |  |  | -17.28% | 2022-11-09 | -164 | 316.5 | 633 | 108743 | 936861 | 936861 | 25 | 23 | 2 | 92.87% | 82.91% | 96.08% | 91.72% | 43.66% | 24.31% | 0% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 17 | 14 | 9 | 5 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 224759024 | 0 | 38224722.34 | 37910212.77 | 37910212.77 | 314509.57 | 224759024
PJ1 | 2021-07-02 | 50.04% | 31.13% | 50.04% | 31.13% |  |  | -18.91% | 2022-11-16 | -166 | 325.5 | 651 | 112625 | 971799 | 971799 | 28 | 27 | 1 | 93.04% | 86.73% | 96.58% | 92.13% | 46.59% | 25.3% | 0.19% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 17 | 14 | 5 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 0 |  | 224759024 | 0 | 38224722.34 | 37910212.77 | 37910212.77 | 314509.57 | 224759024
PJ1 | 2021-07-09 | 52.46% | 31.78% | 52.46% | 31.78% |  |  | -20.68% | 2022-11-23 | -171 | 359 | 718 | 117419 | 1014945 | 1014945 | 28 | 27 | 1 | 93.21% | 87.55% | 97.08% | 92.19% | 49.35% | 26.03% | 1.31% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 5 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 224759024 | 0 | 38224722.34 | 37910212.77 | 37910212.77 | 314509.57 | 224759024
PJ1 | 2021-07-16 | 54.92% | 32.55% | 54.92% | 32.55% |  |  | -22.37% | 2022-11-30 | -178 | 359 | 718 |  |  |  | 29 | 28 | 1 | 93.21% | 87.55% | 97.08% | 92.19% | 49.35% | 26.03% | 1.31% | 0% | [23 empty] | 19 | 14 | 5 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 | [6 empty] | 0 | 0
PJ1 | 2021-07-23 | 56.04% | 32.86% | 56.04% | 32.86% |  |  | -23.18% | 2022-12-07 | -179 | 356.5 | 713 | 124610 | 1079664 | 1079664 | 29 | 28 | 1 | 93.47% | 88% | 97.83% | 92.25% | 53.38% | 27.26% | 3.31% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 5 | 9 |  | 0 | 0 | 0 | 0 |  |  | 9 | 8 | 7 | 9 |  | 224759024 | 0 | 46648042.69 | 42675561.61 | 42675561.61 | 3972481.08 | 224759024
PJ1 | 2021-07-30 | 58.07% | 36.48% | 58.07% | 36.48% |  |  | -21.59% | 2022-12-13 | -179 | 356.5 | 713 | 124610 | 1079664 | 1079664 | 29 | 28 | 1 | 93.47% | 88% | 97.83% | 92.25% | 53.38% | 27.26% | 3.31% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 5 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 224759024 | 0 | 46268707.74 | 42675561.61 | 42675561.61 | 3593146.13 | 224759024
PJ1 | 2021-08-06 | 64.81% | 41.3% | 64.81% | 41.3% |  |  | -23.51% | 2022-12-21 | -192 | 356.5 | 713 | 134198 | 1165956 | 1165956 | 29 | 29 | 0 | 93.81% | 88.33% | 98.74% | 93.11% | 57.62% | 27.88% | 7.49% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 5 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 224759024 | 0 | 46268707.74 | 42675561.61 | 42675561.61 | 3593146.13 | 224759024
PJ1 | 2021-08-13 | 66.41% | 41.39% | 66.41% | 41.39% |  |  | -25.02% | 2022-12-12 | -199 | 356.5 | 713 | 139160 | 1210614 | 1210614 | 31 | 29 | 2 | 93.98% | 88.67% | 99.03% | 93.2% | 59.67% | 28.03% | 8.45% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 5 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 224759024 | 0 | 46268707.74 | 42675561.61 | 42675561.61 | 3593146.13 | 224759024
PJ1 | 2021-08-20 | 68.23% | 41.43% | 68.23% | 41.43% |  |  | -26.8% | 2022-12-26 | -205 | 343 | 686 | 144164 | 1255650 | 1255650 | 32 | 31 | 1 | 94.15% | 89.09% | 99.29% | 93.51% | 62.01% | 28.09% | 9.42% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 5 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 224759024 | 0 | 46268707.74 | 42675561.61 | 42675561.61 | 3593146.13 | 224759024
PJ1 | 2021-08-27 | 70.49% | 41.79% | 70.49% | 41.79% |  |  | -28.7% | 2023-01-02 | -206 | 285 | 570 | 148442 | 1294152 | 1294152 | 32 | 31 | 1 | 94.32% | 89.7% | 99.53% | 94.27% | 64.97% | 28.19% | 10.12% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 7 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 224759024 | 0 | 46268707.74 | 42675561.61 | 42675561.61 | 3593146.13 | 224759024
PJ1 | 2021-09-03 | 72.91% | 42.11% | 72.91% | 42.11% |  |  | -30.8% | 2023-01-08 | -221 | 282.5 | 565 | 152720 | 1332654 | 1332654 | 32 | 31 | 1 | 94.49% | 90.73% | 99.74% | 95.03% | 68.12% | 28.39% | 11.63% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 7 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 224759024 | 0 | 46268707.74 | 42675561.61 | 42675561.61 | 3593146.13 | 224759024
PJ1 | 2021-09-10 | 75.61% | 42.64% | 75.61% | 42.64% |  |  | -32.97% | 2023-01-14 | -227 | 282.5 | 565 | 157004 | 1371210 | 1371210 | 33 | 32 | 1 | 94.66% | 91.21% | 99.86% | 95.77% | 71.65% | 28.88% | 13.97% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 7 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 224759024 | 0 | 46268707.74 | 42675561.61 | 42675561.61 | 3593146.13 | 224759024
PJ1 | 2021-09-17 | 78.34% | 43.21% | 78.34% | 43.21% |  |  | -35.13% | 2023-01-21 | -234 | 455 | 910 | 163508 | 1429746 | 1429746 | 33 | 32 | 1 | 94.83% | 91.74% | 99.94% | 95.82% | 75.18% | 29.62% | 18.45% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 7 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 224759024 | 0 | 46268707.74 | 42675561.61 | 42675561.61 | 3593146.13 | 224759024
PJ1 | 2021-09-24 | 80.64% | 43.96% | 80.64% | 43.96% |  |  | -36.68% | 2023-01-28 | -241 | 470 | 940 | 171134 | 1498380 | 1498380 | 33 | 32 | 1 | 95% | 92.45% | 99.99% | 96.38% | 78.13% | 30.46% | 22.93% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 19 | 14 | 7 | 9 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 7 | 9 |  | 224759024 | 0 | 48629783 | 48629783 | 48629783 | 0 | 224759024
PJ1 | 2021-10-01 | 83.31% | 44.72% | 83.31% | 44.72% |  |  | -38.59% | 2023-02-04 | -256 | 478 | 956 | 177776 | 1558158 | 1558158 | 38 | 37 | 1 | 95.18% | 92.92% | 100% | 96.45% | 81.57% | 31.44% | 28.47% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Engineering and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 20 | 17 | 7 | 11 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 8 | 9 |  | 224759024 | 0 | 48629783 | 48629783 | 48629783 | 0 | 224759024
PJ1 | 2021-10-08 | 86.05% | 45.51% | 86.05% | 45.51% |  |  | -40.54% | 2023-02-09 | -263 | 469.5 | 939 | 184442 | 1618152 | 1618152 | 39 | 23 | 16 | 95.35% | 92.92% | 100% | 96.52% | 85.03% | 32.49% | 36.24% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Procurement and Constrution of Retaining Wall | Contractor must expedite the process and ensure the Subcontractor is on board | 20 | 17 | 7 | 11 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 8 | 9 |  | 224759024 | 0 | 48629783 | 48629783 | 48629783 | 0 | 224759024
PJ1 | 2021-10-15 | 88.77% | 46.69% | 88.77% | 46.69% |  |  | -42.08% | 2023-02-19 | -270 | 337.5 | 675 | 189416 | 1662918 | 1662918 | 39 | 25 | 14 | 95.52% | 92.92% | 100% | 96.52% | 88.46% | 34.08% | 44.79% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Procurement and Constrution of Retaining Wall | Contractor must expedite the process and commence the work | 20 | 17 | 7 | 11 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 224759024 | 0 | 48629783 | 48629783 | 48629783 | 0 | 224759024
PJ1 | 2021-10-22 | 91.37% | 48.2% | 91.37% | 48.2% |  |  | -43.17% | 2023-02-21 | -277 | 428 | 856 | 195488 | 1717566 | 1717566 | 39 | 25 | 14 | 95.69% | 93.24% | 100% | 96.52% | 91.46% | 36.09% | 56.26% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Procurement and Constrution of Retaining Wall | Contractor must expedite the process and commence the work | 20 | 17 | 7 | 11 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 224759024 | 0 | 51550077 | 48629783 | 51550077 | 2920294 | 224759024
PJ1 | 2021-10-29 | 93.59% | 49.7% | 93.59% | 49.7% |  |  | -43.89% | 2023-02-27 | -284 | 337.5 | 675 | 201608 | 1772646 | 1772646 | 39 | 25 | 14 | 95.91% | 93.53% | 100% | 97.24% | 94.33% | 37.91% | 67.72% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Procurement and Constrution of Retaining Wall | Contractor must expedite the process and commence the work | 21 | 17 | 7 | 12 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 224759024 | 0 | 51550077 | 48629783 | 51550077 | 2920294 | 224759024
PJ1 | 2021-11-05 | 95.01% | 51.25% | 95.01% | 51.25% |  |  | -43.76% | 2023-03-06 | -291 | 312.5 | 625 | 207494 | 1825620 | 1825620 | 47 | 37 | 10 | 96.19% | 93.53% | 100% | 97.24% | 95.99% | 40% | 76.12% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Procurement and Constrution of Retaining Wall | Contractor must expedite the process and commence the work | 21 | 17 | 7 | 12 |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 224759024 | 0 | 51550077 | 48629783 | 51550077 | 2920294 | 224759024
PJ1 | 2021-11-12 | 96.07% | 52.76% | 96.07% | 52.76% |  |  | -43.31% | 2023-03-13 | -297 | 312.5 | 625 | 213260 | 1877514 | 1877514 | 47 | 37 | 10 | 96.47% | 93.85% | 100% | 97.53% | 97.12% | 41.94% | 83.61% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Procurement and Constrution of Retaining Wall | Contractor must expedite the process and commence the work | 21 | 17 | 7 | 12 |  | 1 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 224759024 | 0 | 51550077 | 48629783 | 51550077 | 2920294 | 224759024
PJ1 | 2021-11-19 | 96.78% | 54.37% | 96.78% | 54.37% |  |  | -42.41% | 2023-03-20 | -305 | 312.5 | 625 | 217376 | 1914558 | 1914558 | 48 | 39 | 9 | 96.74% | 94.52% | 100% | 98.31% | 97.86% | 43.88% | 87.66% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Procurement and Constrution of Retaining Wall | Contractor must expedite the process and commence the work | 21 | 17 | 7 | 12 |  | 1 | 0 | 0 | 0 |  |  | 8 | 8 | 6 | 8 |  | 224759024 | 0 | 51550077 | 48629783 | 51550077 | 2920294 | 224759024
PJ1 | 2021-11-26 | 97.29% | 55.78% | 97.29% | 55.78% |  |  | -41.51% | 2023-03-28 | -296 | 312.5 | 625 | 221492 | 1951602 | 1951602 | 48 | 39 | 9 | 97.02% | 94.52% | 100% | 99.8% | 98.4% | 45.37% | 90.08% | 0% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Procurement and Constrution of Retaining Wall | Contractor must expedite the process and commence the work | 22 | 17 | 7 | 13 |  | 1 | 0 | 0 | 0 |  |  | 9 | 8 | 6 | 8 |  | 224759024 | 6046633 | 51550077 | 48629783 | 51550077 | 2920294 | 230805657
PJ1 | 2021-12-03 | 97.68% | 56.99% | 97.68% | 56.99% |  |  | -40.69% | 2023-04-05 | -310 | 262 | 524 | 225608 | 1988646 | 1988646 | 48 | 39 | 9 | 97.3% | 94.52% | 100% | 99.8% | 98.74% | 46.83% | 93.29% | 5.97% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Procurement and Constrution of Retaining Wall | Contractor must expedite the process and commence the work | 22 | 17 | 7 | 13 |  | 1 | 0 | 0 | 0 |  |  | 9 | 8 | 6 | 8 |  | 224759024 | 6046633 | 56013983 | 48629783 | 54463967 | 7384200 | 230805657 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2021-12-10 | 98.01% | 58.24% | 98.01% | 58.24% |  |  | -39.77% | 2023-04-12 | -317 | 262 | 524 | 231284 | 2039730 | 2039730 | 50 | 41 | 9 | 97.59% | 95.1% | 100% | 99.8% | 99.02% | 48.5% | 95.8% | 5.97% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Procurement and Constrution of Retaining Wall | Contractor must expedite the process and commence the work | 22 | 17 | 7 | 13 |  | 1 | 0 | 0 | 0 |  |  | 9 | 8 | 6 | 8 |  | 224759024 | 6046633 | 56013983 | 48629783 | 54463967 | 7384200 | 230805657 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2021-12-17 | 98.33% | 60.98% | 98.33% | 60.98% |  |  | -37.35% | 2023-04-20 | -323 | 262 | 524 | 236648 | 2088006 | 2088006 | 50 | 43 | 7 | 97.95% | 95.1% | 100% | 99.8% | 99.3% | 52.18% | 97.62% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 7 | 13 |  | 1 | 0 | 0 | 0 |  |  | 9 | 8 | 6 | 8 |  | 224759024 | 6046633 | 56013983 | 48629783 | 54463967 | 7384200 | 230805657 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2021-12-24 | 98.56% | 61.74% | 98.56% | 61.74% |  |  | -36.82% | 2023-04-27 | -329 | 262 | 524 | 242114 | 2137200 | 2137200 | 50 | 43 | 7 | 98.24% | 95.1% | 100% | 99.8% | 99.5% | 53.2% | 98.59% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 7 | 13 |  | 1 | 0 | 0 | 0 |  |  | 9 | 8 | 6 | 8 |  | 224759024 | 6046633 | 63495725 | 54463964 | 58303034 | 9031761 | 230805657 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2021-12-31 | 98.81% | 61.74% | 98.81% | 61.74% |  |  | -37.07% | 2023-05-03 | -336 | 262 | 524 | 247580 | 2186394 | 2186394 | 50 | 43 | 7 | 98.24% | 95.1% | 100% | 99.8% | 99.5% | 53.2% | 98.59% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 1 | 13 |  | 2 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 224759024 | 6046633 | 63495725 | 54463964 | 58303034 | 9031761 | 230805657 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-01-07 | 99% | 63.13% | 99% | 63.13% |  |  | -35.87% | 2023-05-23 | -343 | 262 | 524 | 252428 | 2230026 | 2230026 | 50 | 43 | 7 | 99.11% | 95.1% | 100% | 99.8% | 99.79% | 55.07% | 99.77% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 1 | 13 |  | 2 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 224759024 | 6046633 | 63495725 | 54463964 | 58303034 | 9031761 | 230805657 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-01-14 | 99.19% | 64.04% | 99.19% | 64.04% |  |  | -35.15% | 2023-05-23 | -350 | 262 | 524 | 257354 | 2274360 | 2274360 | 50 | 41 | 9 | 99.39% | 95.1% | 100% | 99.8% | 100% | 68.93% | 99.95% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 1 | 13 |  | 2 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 224759024 | 6046633 | 63495725 | 54463964 | 58303034 | 9031761 | 230805657 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-01-21 | 99.34% | 64.8% | 99.34% | 64.8% |  |  | -34.54% | 2023-05-23 | -355 | 262 | 524 | 262280 | 2318694 | 2318694 | 50 | 41 | 9 | 99.57% | 95.1% | 100% | 99.8% | 100% | 57.32% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 1 | 13 |  | 2 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 224759024 | 6046633 | 66082016.81 | 58303034.29 | 66082016.81 | 7778982.52 | 230805657 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-01-28 | 99.47% | 65.56% | 99.47% | 65.56% |  |  | -33.91% | 2023-05-30 | -365 | 262 | 524 | 267182 | 2362812 | 2362812 | 50 | 41 | 9 | 99.77% | 95.1% | 100% | 99.8% | 100% | 58.34% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open | Second Wave of Covid-19 | Contractor to take all necessary measures to minimize the risk of outbreak | Contractor | Open | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 1 | 13 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 224759024 | 6046633 | 66082016.81 | 58303034.29 | 66082016.81 | 7778982.52 | 230805657 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-02-04 | 99.57% | 66.26% | 99.57% | 66.26% |  |  | -33.31% | 2023-06-06 | -367 | 262 | 524 | 272078 | 2406876 | 2406876 | 50 | 41 | 9 | 99.88% | 95.1% | 100% | 99.8% | 100% | 59.28% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 1 | 13 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 224759024 | 5509015.65 | 103215355.94 | 66082016 | 103215355.94 | 37133339.94 | 230268039.65 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-02-11 | 99.72% | 66.96% | 99.72% | 66.96% |  |  | -32.76% | 2023-06-13 | -373 | 262 | 524 | 276920 | 2450454 | 2450454 | 50 | 41 | 9 | 99.95% | 95.1% | 100% | 99.8% | 100% | 60.22% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 1 | 13 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 224759024 | 5509015.65 | 103215355.94 | 66082016 | 103215355.94 | 37133339.94 | 230268039.65 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-02-18 | 99.96% | 67.66% | 99.96% | 67.66% |  |  | -32.3% | 2023-05-27 | -380 | 262 | 524 | 281762 | 2494032 | 2494032 | 50 | 41 | 9 | 100% | 95.1% | 100% | 99.8% | 100% | 61.17% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 1 | 13 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 224759024 | 5509015.65 | 103215355.94 | 66082016 | 103215355.94 | 37133339.94 | 230268039.65 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-02-25 | 100% | 68.28% | 100% | 68.28% |  |  | -31.72% | 2023-06-03 | -387 | 216.5 | 433 | 286592 | 2537502 | 2537502 | 50 | 41 | 9 | 100% | 95.1% | 100% | 99.8% | 100% | 62% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 1 | 13 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 224759024 | 5509015.65 | 103215355.94 | 66082016 | 103215355.94 | 37133339.94 | 230268039.65 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-03-04 | 100% | 68.78% | 100% | 68.78% |  |  | -31.22% | 2023-06-10 | -394 | 246.5 | 493 | 289574 | 2564340 | 2564340 | 50 | 41 | 9 | 100% | 95.62% | 100% | 99.8% | 100% | 62.66% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 22 | 17 | 1 | 13 |  | 3 | 0 | 0 | 0 |  |  | 10 | 8 | 6 | 8 |  | 224759024 | 5509015.65 | 103215355.94 | 66082016 | 103215355.94 | 37133339.94 | 230268039.65 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-03-11 | 100% | 69.38% | 100% | 69.38% |  |  | -30.62% | 2023-06-17 | -402 | 246.5 | 493 | 292550 | 2591124 | 2591124 | 50 | 41 | 9 | 100% | 95.62% | 100% | 99.92% | 100% | 63.47% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 224759024 | 5509015.65 | 103215355.94 | 66082016 | 103215355.94 | 37133339.94 | 230268039.65 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-03-18 | 100% | 70.03% | 100% | 70.03% |  |  | -29.97% | 2023-06-24 | -410 | 246.5 | 493 | 295532 | 2617962 | 2617962 | 50 | 41 | 9 | 100% | 96.01% | 100% | 99.8% | 100% | 64.33% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 224759024 | 11380179.96 | 128294251.93 | 103215355.94 | 128294251.93 | 25078895.99 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-03-25 | 100% | 71.23% | 100% | 71.23% |  |  | -28.77% | 2023-07-01 | -417 | 246.5 | 493 | 298520 | 2644854 | 2644854 | 50 | 41 | 9 | 100% | 96.01% | 100% | 99.8% | 100% | 65.94% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 224759024 | 11380179.96 | 128294251.93 | 103215355.94 | 128294251.93 | 25078895.99 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-04-01 | 100% | 71.23% | 100% | 71.23% |  |  | -28.77% | 2023-07-06 | -425 | 246.5 | 493 | 301514 | 2671800 | 2671800 | 50 | 41 | 9 | 100% | 96.06% | 100% | 99.81% | 100% | 67.14% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 224759024 | 11380179.96 | 128294251.93 | 103215355.94 | 128294251.93 | 25078895.99 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-04-08 | 100% | 72.98% | 100% | 72.98% |  |  | -27.02% | 2023-06-24 | -432 | 246.5 | 493 | 304502 | 2698692 | 2698692 | 50 | 41 | 9 | 100% | 96.06% | 100% | 99.81% | 100% | 68.18% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 224759024 | 11380179.96 | 128294251.93 | 103215355.94 | 128294251.93 | 25078895.99 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-04-15 | 100% | 73.49% | 100% | 73.49% |  |  | -26.51% | 2023-06-30 | -438 | 246.5 | 493 | 307484 | 2716584 | 2716584 | 50 | 41 | 9 | 100% | 96.06% | 100% | 99.81% | 100% | 68.9% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 224759024 | 11380179.96 | 138844021 | 128294251.93 | 138844021 | 10549769.07 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-04-22 | 100% | 74.09% | 100% | 74.09% |  |  | -25.91% | 2023-07-13 | -458 | 246.5 | 493 | 310472 | 2734512 | 2734512 | 50 | 41 | 9 | 100% | 96.12% | 100% | 99.81% | 100% | 69.66% | 100% | 6.28% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 224759024 | 11380179.96 | 138844021 | 138844021 | 138844021 | 0 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-04-29 | 100% | 74.5% | 100% | 74.5% |  |  | -25.5% | 2023-07-20 | -458 | 246.5 | 493 | 310472 | 2734512 | 2734512 | 50 | 41 | 9 | 100% | 96.12% | 100% | 99.81% | 100% | 70.22% | 100% | 10.33% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 224759024 | 11380179.96 | 138844021 | 138844021 | 138844021 | 0 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-05-06 | 100% | 74.6% | 100% | 74.6% |  |  | -25.4% | 2023-07-13 | -458 | 246.5 | 493 | 314945 | 2762841 | 2762841 | 50 | 41 | 9 | 100% | 96.12% | 100% | 99.81% | 100% | 70.36% | 100% | 10.33% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 224759024 | 11380179.96 | 138844021 | 138844021 | 138844021 | 0 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-05-13 | 100% | 75.2% | 100% | 75.2% |  |  | -24.8% | 2023-06-28 | -465 | 246.5 | 493 | 317927 | 2789679 | 2789679 | 50 | 41 | 9 | 100% | 96.12% | 100% | 99.81% | 100% | 71.17% | 100% | 10.33% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 12 | 9 | 5 | 8 |  | 224759024 | 11380179.96 | 138844021 | 138844021 | 138844021 | 0 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-05-20 | 100% | 75.91% | 100% | 75.91% |  |  | -24.09% | 2023-05-25 | -472 | 246.5 | 493 | 320903 | 2816463 | 2816463 | 50 | 41 | 9 | 100% | 96.12% | 100% | 99.81% | 100% | 72.12% | 100% | 10.33% | North R/A - Temporary access to Qetifian Island is within the project boundary | Ensure the area is avaialble for Contractor | Client | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 224759024 | 11380179.96 | 138844021 | 138844021 | 138844021 | 0 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-05-27 | 100% | 76.91% | 100% | 76.91% |  |  | -23.09% | 2023-05-23 | -479 | 246.5 | 493 | 323879 | 2843247 | 2843247 | 50 | 41 | 9 | 100% | 96.12% | 100% | 99.81% | 100% | 73.47% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 224759024 | 11380179.96 | 143919890 | 138844021 | 143902890 | 5075869 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-06-03 | 100% | 77.25% | 100% | 77.25% |  |  | -22.75% | 2023-05-27 | -462 | 160.5 | 321 | 326849 | 2869977 | 2869977 | 50 | 41 | 9 | 100% | 96.12% | 100% | 99.81% | 100% | 73.92% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 224759024 | 11380179.96 | 143919890 | 138844021 | 143902890 | 5075869 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-06-10 | 100% | 77.25% | 100% | 77.25% |  |  | -22.75% | 2023-06-01 | -469 | 158 | 316 | 329813 | 2896653 | 2896653 | 50 | 41 | 9 | 100% | 96.12% | 100% | 99.81% | 100% | 74.38% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 224759024 | 11380179.96 | 143919890 | 138844021 | 143902890 | 5075869 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-06-17 | 100% | 77.89% | 100% | 77.89% |  |  | -22.11% | 2023-06-14 | -476 | 158 | 316 | 332771 | 2923275 | 2923275 | 50 | 41 | 9 | 100% | 96.12% | 100% | 99.81% | 100% | 74.77% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 224759024 | 11380179.96 | 143919890 | 143919890 | 143902890 | 0 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-06-24 | 100% | 78.14% | 100% | 78.14% |  |  | -21.86% | 2023-06-18 | -483 | 158 | 316 | 335693 | 2949573 | 2949573 | 50 | 41 | 9 | 100% | 96.12% | 100% | 99.81% | 100% | 75.25% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 224759024 | 11380179.96 | 143919890 | 143919890 | 143902890 | 0 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-07-01 | 100% | 78.59% | 100% | 78.59% |  |  | -21.41% | 2023-01-01 | -490 | 158 | 316 | 338579 | 2975547 | 2975547 | 50 | 41 | 9 | 100% | 96.17% | 100% | 99.9% | 100% | 75.7% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 3 |  |  | 13 | 11 | 5 | 9 |  | 224759024 | 11380179.96 | 143919890 | 143919890 | 143902890 | 0 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-07-08 | 100% | 78.59% | 100% | 78.59% |  |  | -21.41% | 2023-01-08 | -497 | 151.5 | 303 | 341447 | 3001359 | 3001359 | 50 | 41 | 9 | 100% | 96.17% | 100% | 99.9% | 100% | 75.7% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 13 | 11 | 5 | 9 |  | 224759024 | 11380179.96 | 143919890 | 143919890 | 143902890 | 0 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-07-15 | 100% | 79% | 76.6% | 76.6% |  |  | 0% | 2023-01-21 | -502 | 151.5 | 303 | 342845 | 3013941 | 3013941 | 50 | 41 | 9 | 100% | 96.17% | 100% | 99.9% | 100% | 76.24% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 11380179.96 | 143919890 | 143919890 | 143902890 | 0 | 236139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-07-22 | 100% | 79.3% | 77.67% | 77.69% |  |  | 0.02466% | 2023-01-21 | -490 | 148 | 296 | 345647 | 3039159 | 3039159 | 50 | 41 | 9 | 100% | 96.17% | 100% | 99.9% | 100% | 76.65% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 152902890.74 | 143919890 | 152902890.74 | 8983000.74 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-07-29 | 100% | 79.55% | 78.46% | 77.95% |  |  | -0.5138% | 2023-01-29 | -496 | 149 | 298 | 348437 | 3064269 | 3064269 | 50 | 41 | 9 | 100% | 96.17% | 100% | 99.9% | 100% | 76.99% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Pososibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 152902890.74 | 143919890 | 152902890.74 | 8983000.74 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-08-05 | 100% | 79.89% | 79.17% | 78.3% |  |  | -0.8618% | 2023-02-05 | -509 | 149 | 298 | 350447 | 3082359 | 3082359 | 50 | 41 | 9 | 100% | 96.17% | 100% | 99.9% | 100% | 77.44% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 152902890.74 | 143919890 | 152902890.74 | 8983000.74 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-08-12 | 100% | 80.3% | 79.61% | 78.69% |  |  | -0.9173% | 2023-02-12 | -516 | 179 | 358 | 353435 | 3102951 | 3102951 | 50 | 41 | 9 | 100% | 96.17% | 100% | 99.9% | 100% | 78% | 100% | 10.33% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 152902890.74 | 143919890 | 152902890.74 | 8983000.74 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-08-19 | 100% | 80.86% | 80.1% | 79.12% |  |  | -0.9817% | 2023-02-20 | -509 | 182 | 364 | 35623 | 3133443 | 3133443 | 52 | 52 | 0 | 100% | 96.17% | 100% | 99.9% | 100% | 78.72% | 100% | 11.57% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 152902890.74 | 143919890 | 152902890.74 | 8983000.74 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-08-25 | 100% | 81.88% | 80.68% | 79.62% |  |  | -1.057% | 2023-02-27 | -494 | 182 | 364 | 358907 | 3158507 | 3158507 | 52 | 52 | 0 | 100% | 96.17% | 100% | 99.9% | 100% | 80.05% | 100% | 12.7% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions due to Dewatering tanks | Dewatering tanks of other contractors to be removed | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 152902890.74 | 143919890 | 152902890.74 | 8983000.74 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-09-01 | 100% | 82.49% | 81.22% | 80.42% |  |  | -0.8047% | 2023-03-06 | -460 | 182 | 364 | 361625 | 3182969 | 3182969 | 52 | 52 | 0 | 100% | 96.17% | 100% | 99.93% | 100% | 80.86% | 100% | 13.12% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions in Lateral streets near North | Area to be cleared and handedover to Contractor | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 152902890.74 | 143919890 | 152902890.74 | 8983000.74 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-09-08 | 100% | 83.33% | 81.73% | 81.69% |  |  | -0.04438% | 2023-05-30 | -458 | 133 | 266 | 364379 | 3207755 | 3207755 | 52 | 52 | 0 | 100% | 96.5% | 100% | 99.94% | 100% | 81.94% | 100% | 14.56% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions in Lateral streets near North | Area to be cleared and handedover to Contractor | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 152902890.74 | 143919890 | 152902890.74 | 8983000.74 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-09-15 | 100% | 84.01% | 82.37% | 83.07% |  |  | 0.6995% | 2023-05-30 | -462 | 133 | 266 | 364379 | 3207755 | 3207755 | 52 | 52 | 0 | 100% | 96.53% | 100% | 99.94% | 100% | 82.82% | 100% | 15.62% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  |  | Road East handover | Other Contractor should release the area without further delay | Obstructions due to Other Contractor | Areas are obstructed by PJ33 contractor in Doha North | Consultant/Client to ensure the area is avaialble for Contractor | Site Obstructions | Obstructions in Lateral streets near North | Area to be cleared and handedover to Contractor | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 152902890.74 | 143919890 | 152902890.74 | 8983000.74 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-09-22 | 100% | 84.27% | 84.42% | 85.15% |  |  | 0.7289% | 2023-05-22 | -467 | 181 | 362 | 370547 | 3263267 | 3263267 | 55 | 52 | 3 | 100% | 96.53% | 100% | 99.94% | 100% | 83.17% | 100% | 15.62% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be cleared and handedover to Contractor | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process |  |  |  | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 152902890.74 | 143919890 | 152902890.74 | 8983000.74 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-09-29 | 100% | 85.13% | 86.64% | 86.77% |  |  | 0.1264% | 2023-05-20 | -480 | 181 | 362 | 373967 | 3294047 | 3294047 | 56 | 52 | 4 | 100% | 96.59% | 100% | 99.94% | 100% | 84.29% | 100% | 16.38% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be cleared and handedover to Contractor | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process |  |  |  | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 143919890 | 188905762.6 | 44985872.6 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-10-06 | 100% | 86.69% | 89.17% | 89.19% |  |  | 0.01954% | 2023-05-21 | -484 | 181 | 362 | 376961 | 3320993 | 3320993 | 57 | 52 | 5 | 100% | 96.64% | 100% | 99.94% | 100% | 86.35% | 100% | 17.58% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be cleared and handedover to Contractor | Delay in Retaining Wall | Contractor is delayed in Construction of Retaining Wall | Contractor must expedite work | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process |  |  |  | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 169380348.6 | 188905762.6 | 19525414 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-10-13 |  |  | 92.97% | 91.01% |  |  | -1.958% | 2023-05-27 | -52 | 190 | 380 | 379787 | 3346427 | 3346427 | 57 | 53 | 4 | 100% | 100% | 99.93% | 99.92% | 93.37% | 90.98% | 24.9% | 20.35% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 169380348.6 | 188905762.6 | 19525414 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-10-20 |  |  | 96.54% | 92.03% |  |  | -4.511% | 2023-05-31 | -59 | 205 | 410 | 382601 | 3371753 | 3371753 | 58 | 55 | 3 | 100% | 100% | 99.93% | 99.92% | 93.37% | 90.98% | 24.9% | 20.35% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 169380348.6 | 188905762.6 | 19525414 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-10-27 |  |  | 98.46% | 92.64% |  |  | -5.819% | 2023-06-06 | -72 | 211 | 422 | 385811 | 3400643 | 3400643 | 58 | 55 | 3 | 100% | 100% | 100% | 99.92% | 99.56% | 93% | 67.56% | 32.26% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 169380348.6 | 188905762.6 | 19525414 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-11-03 |  |  | 99.43% | 93.03% |  |  | -6.398% | 2023-06-05 | -72 | 211 | 422 | 389639 | 3435095 | 3435095 | 58 | 55 | 3 | 100% | 100% | 100% | 99.92% | 99.82% | 93% | 68.56% | 32.26% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 169380348.6 | 188905762.6 | 19525414 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-11-10 |  |  | 100% | 93.33% |  |  | -6.67% | 2023-06-07 | -80 | 211 | 422 | 393209 | 3467225 | 3467225 | 60 | 55 | 5 | 100% | 100% | 100% | 99.94% | 100% | 93.82% | 100% | 39.09% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 169380348.6 | 188905762.6 | 19525414 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-11-17 |  |  | 100% | 93.54% |  |  | -6.46% | 2023-06-11 | -87 | 211 | 422 | 396275 | 3494819 | 3494819 | 60 | 55 | 5 | 100% | 100% | 100% | 99.94% | 100% | 94.03% | 100% | 39.22% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 169380348.6 | 188905762.6 | 19525414 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-11-24 |  |  | 100% | 93.6% |  |  | -6.4% | 2023-06-12 | -94 | 211 | 422 | 397385 | 3504809 | 3504809 | 60 | 55 | 5 | 100% | 100% | 100% | 99.94% | 100% | 94.17% | 100% | 39.93% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 169380348.6 | 188905762.6 | 19525414 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-12-01 |  |  | 100% | 93.66% |  |  | -6.34% | 2023-09-30 | -102 | 211 | 422 | 398279 | 3512855 | 3512855 | 60 | 55 | 5 | 100% | 100% | 100% | 99.94% | 100% | 94.17% | 100% | 39.93% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 169380348.6 | 188905762.6 | 19525414 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-12-08 |  |  | 100% | 93.66% |  |  | -6.34% | 2023-10-07 | -109 | 211 | 422 | 399101 | 3520253 | 3520253 | 60 | 55 | 5 | 100% | 100% | 100% | 99.94% | 100% | 94.17% | 100% | 39.93% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 20380179.96 | 188905762.6 | 169380348.6 | 188905762.6 | 19525414 | 245139203.96 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-12-15 |  |  | 100% | 93.66% |  |  | -6.34% | 2023-10-12 | -116 | 211 | 422 | 399899 | 3527435 | 3527435 | 60 | 55 | 5 | 100% | 100% | 100% | 99.94% | 100% | 94.17% | 100% | 39.93% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-12-22 |  |  | 89.83% | 89.92% |  |  | 0.09257% | 2023-10-18 | -78 | 105 | 210 | 400997 | 3537317 | 3537317 | 60 | 55 | 5 | 99.98% | 99.2% | 99.52% | 99.26% | 88.64% | 88.99% | 18.08% | 25.02% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2022-12-29 |  |  | 90.65% | 90.84% |  |  | 0.1858% | 2023-10-30 | -78 | 105 | 210 | 402131 | 3547523 | 3547523 | 60 | 55 | 5 | 99.98% | 99.2% | 99.52% | 99.26% | 88.64% | 88.99% | 18.08% | 25.02% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-01-05 |  |  | 91.4% | 91.46% |  |  | 0.0626% | 2023-10-30 | -70 | 105 | 210 | 403733 | 3561941 | 3561941 | 60 | 55 | 5 | 99.99% | 99.52% | 99.7% | 99.73% | 91.04% | 91.02% | 18.08% | 25.02% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-01-12 |  |  | 92.18% | 92.26% |  |  | 0.07812% | 2023-11-18 | -68 | 105 | 210 | 405359 | 3576575 | 3561941 | 63 | 55 | 8 | 99.99% | 99.52% | 99.77% | 99.78% | 92.14% | 92.08% | 18.08% | 28.95% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Site Obstructions | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-01-19 |  |  | 92.91% | 92.57% |  |  | -0.3378% | 2023-11-20 | -69 | 105 | 210 | 407009 | 3591425 | 3591425 | 63 | 55 | 8 | 100% | 99.72% | 99.84% | 99.78% | 93.16% | 92.5% | 18.08% | 29.37% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-01-26 |  |  | 93.71% | 93.06% |  |  | -0.6506% | 2023-11-27 | -75 | 100 | 200 | 408659 | 3606275 | 3606275 | 65 | 56 | 9 | 100% | 99.81% | 99.9% | 99.8% | 94.29% | 93.19% | 18.08% | 29.58% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-02-02 |  |  | 94.63% | 93.31% |  |  | -1.324% | 2023-11-30 | -79 | 100 | 200 | 410231 | 3620423 | 3620423 | 68 | 56 | 12 | 100% | 99.81% | 99.94% | 99.81% | 95.56% | 93.51% | 20.35% | 29.65% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 4 | 0 | 0 | 4 |  |  | 14 | 11 | 5 | 9 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-02-09 |  |  | 95.77% | 93.55% |  |  | -2.218% | 2023-11-30 | -85 | 100 | 200 | 411791 | 3634463 | 3634463 | 69 | 57 | 12 | 100% | 99.81% | 99.97% | 99.84% | 96.79% | 93.82% | 33.08% | 29.87% | Possiblilty of other contractors damaging/obstructing the work | Ensure the limit of works is protected by the Contractor | Contractor | Open | Possibilty of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Consultant/Client | Open |  |  |  | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-02-16 |  |  | 97.01% | 93.8% |  |  | -3.207% | 2023-11-30 | -84 | 70 | 140 | 412831 | 3643823 | 3643823 | 70 | 58 | 12 | 100% | 99.81% | 99.99% | 99.84% | 98.1% | 94.16% | 47.52% | 29.94% | Site Obstructions: Risk of affecting the critical path by obstructions late clearance. Potential EOT Entitlement. | Coordination with all stakeholders and Client Logistics. | ALL | Open | Procurement / Long Lead Items: Risk of affecting the critical path due to procurement delays. Project Completion Delay risk. | Procurement to be closely monitored. | Contractor | Open | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-02-23 |  |  | 98.42% | 93.94% |  |  | -4.48% | 2023-12-02 | -86 | 48 | 96 | 414037 | 3654677 | 3654677 | 70 | 58 | 12 | 100% | 99.81% | 100% | 99.84% | 99.46% | 94.34% | 70.08% | 30.02% | Site Obstructions: Risk of affecting the critical path by obstructions late clearance. Potential EOT Entitlement. | Coordination with all stakeholders and Client Logistics. | ALL | Open | Procurement / Long Lead Items: Risk of affecting the critical path due to procurement delays. Project Completion Delay risk. | Procurement to be closely monitored. | Contractor | Open | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-03-02 |  |  | 99.35% | 94.09% |  |  | -5.257% | 2023-11-30 | -90 | 50.5 | 101 | 415021 | 3663533 | 3663533 | 71 | 59 | 12 | 100% | 99.81% | 100% | 99.84% | 99.99% | 94.55% | 93.79% | 30.02% | Site Obstructions: Risk of affecting the critical path by obstructions late clearance. Potential EOT Entitlement. | Coordination with all stakeholders and Client Logistics. | ALL | Open | Procurement / Long Lead Items: Risk of affecting the critical path due to procurement delays. Project Completion Delay risk. | Procurement to be closely monitored. | Contractor | Open | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-03-09 |  |  | 99.73% | 94.31% |  |  | -5.424% | 2023-11-30 | -91 | 50.5 | 101 | 416023 | 3672551 | 3672551 | 71 | 61 | 10 | 100% | 99.81% | 100% | 99.84% | 100% | 94.83% | 99.95% | 30.02% | Site Obstructions: Risk of affecting the critical path by obstructions late clearance. Potential EOT Entitlement. | Coordination with all stakeholders and Client Logistics. | ALL | Open | Procurement / Long Lead Items: Risk of affecting the critical path due to procurement delays. Project Completion Delay risk. | Procurement to be closely monitored. | Contractor | Open | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-03-16 |  |  | 100% | 94.56% |  |  | -5.44% | 2023-11-30 | -201 | 0 | 101 | 417001 | 3681353 | 3681353 | 72 | 61 | 11 | 100% | 99.81% | 100% | 99.84% | 100% | 95.15% | 100% | 30.02% | Site Obstructions: Risk of affecting the critical path by obstructions late clearance. Potential EOT Entitlement. | Coordination with all stakeholders and Client Logistics. | ALL | Open | Procurement / Long Lead Items: Risk of affecting the critical path due to procurement delays. Project Completion Delay risk. | Procurement to be closely monitored. | Contractor | Open | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-03-23 |  |  | 100% | 94.7% |  |  | -5.3% | 2023-11-30 | -208 | 0 | 103 | 417985 | 3689717 | 3689717 | 72 | 62 | 10 | 100% | 99.81% | 100% | 99.84% | 100% | 95.33% | 100% | 30.1% | Site Obstructions: Risk of affecting the critical path by obstructions late clearance. Potential EOT Entitlement. | Coordination with all stakeholders and Client Logistics. | ALL | Open | Procurement / Long Lead Items: Risk of affecting the critical path due to procurement delays. Project Completion Delay risk. | Procurement to be closely monitored. | Contractor | Open | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-03-30 |  |  | 100% | 94.83% |  |  | -5.17% | 2023-11-30 | -213 | 0 | 103 | 419017 | 3695909 | 3695909 | 72 | 62 | 10 | 100% | 99.81% | 100% | 99.84% | 100% | 95.5% | 100% | 30.1% | Site Obstructions: Risk of affecting the critical path by obstructions late clearance. Potential EOT Entitlement. | Coordination with all stakeholders and Client Logistics. | ALL | Open | Procurement / Long Lead Items: Risk of affecting the critical path due to procurement delays. Project Completion Delay risk. | Procurement to be closely monitored. | Contractor | Open | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-04-06 |  |  | 100% | 94.94% |  |  | -5.06% | 2023-11-30 | -219 | 0 | 103 | 420025 | 3701957 | 3701957 | 72 | 63 | 9 | 100% | 99.81% | 100% | 99.84% | 100% | 95.64% | 100% | 30.1% | Site Obstructions: Risk of affecting the critical path by obstructions late clearance. Potential EOT Entitlement. | Coordination with all stakeholders and Client Logistics. | ALL | Open | Procurement / Long Lead Items: Risk of affecting the critical path due to procurement delays. Project Completion Delay risk. | Procurement to be closely monitored. | Contractor | Open | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-04-13 |  |  | 100% | 95.02% |  |  | -4.98% | 2023-11-30 | -231 | 0 | 103 | 421039 | 3708041 | 3708041 | 72 | 63 | 9 | 100% | 99.81% | 100% | 99.84% | 100% | 95.73% | 100% | 30.1% | Site Obstructions: Risk of affecting the critical path by obstructions late clearance. Potential EOT Entitlement. | Coordination with all stakeholders and Client Logistics. | ALL | Open | Procurement / Long Lead Items: Risk of affecting the critical path due to procurement delays. Project Completion Delay risk. | Procurement to be closely monitored. | Contractor | Open | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | Lack of manpower to address the open work fornt | Area to be fully cleared and handedover to Contractor | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 35327023 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 260086047 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-04-20 |  |  | 100% | 95.11% |  |  | -4.89% | 2023-11-30 | -231 | 0 | 103 | 422095 | 3714377 | 3714377 | 72 | 64 | 8 | 100% | 99.81% | 100% | 99.84% | 100% | 95.82% | 100% | 30.1% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-04-27 |  |  | 100% | 95.16% |  |  | -4.84% | 2023-11-30 | -250 | 0 | 103 | 422629 | 3719183 | 3719183 | 72 | 64 | 8 | 100% | 99.85% | 100% | 99.86% | 100% | 95.86% | 100% | 31.15% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-05-04 |  |  | 100% | 95.19% |  |  | -4.81% | 2023-11-30 | -252 | 0 | 103 | 423703 | 3728849 | 3728849 | 73 | 64 | 9 | 100% | 99.85% | 100% | 99.86% | 100% | 95.87% | 100% | 31.6% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-05-11 |  |  | 100% | 95.21% |  |  | -4.79% | 2023-11-30 | -259 | 0 | 103 | 424765 | 3738407 | 3738407 | 73 | 64 | 9 | 100% | 99.85% | 100% | 99.87% | 100% | 95.89% | 100% | 32.2% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-05-18 |  |  | 100% | 95.28% |  |  | -4.72% | 2023-11-30 | -262 | 0 | 103 | 425809 | 3747803 | 3747803 | 73 | 64 | 9 | 100% | 99.86% | 100% | 99.87% | 100% | 95.98% | 100% | 32.23% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-05-25 |  |  | 100% | 95.31% |  |  | -4.69% | 2023-11-30 | -262 | 0 | 103 | 426829 | 3756983 | 3756983 | 74 | 64 | 10 | 100% | 99.86% | 100% | 99.87% | 100% | 96.02% | 100% | 32.23% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-06-01 |  |  | 100% | 95.35% |  |  | 0% | 2023-11-30 | -262 | 0 | 103 | 427843 | 3766109 | 3766109 | 75 | 64 | 0 | 100% | 99.86% | 100% | 99.87% | 100% | 96.02% | 100% | 32.23% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 0 | 0 | 0 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-06-08 |  |  | 100% | 95.4% |  |  | -4.6% | 2023-11-30 | -264 | 0 | 103 | 428839 | 3775073 | 3775073 | 75 | 64 | 11 | 100% | 99.87% | 100% | 99.87% | 100% | 96.12% | 100% | 32.87% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-06-15 |  |  | 100% | 95.5% |  |  | -4.5% | 2023-11-30 | -262 | 0 | 113 | 429937 | 3784955 | 3784955 | 76 | 64 | 12 | 100% | 99.87% | 100% | 99.87% | 100% | 96.26% | 100% | 32.87% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-06-22 |  |  | 100% | 95.59% |  |  | -4.41% | 2023-11-30 | -262 | 0 | 109 | 430783 | 3792569 | 3792569 | 76 | 64 | 12 | 100% | 99.87% | 100% | 99.87% | 100% | 96.38% | 100% | 32.87% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-06-29 |  |  | 100% | 95.63% |  |  | -4.37% | 2023-11-30 | -262 | 0 | 92 | 431203 | 3796349 | 3796349 | 76 | 64 | 12 | 100% | 99.87% | 100% | 99.87% | 100% | 96.41% | 100% | 32.87% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-07-06 |  |  | 100% | 95.7% |  |  | -4.3% | 2023-11-30 | -262 | 0 | 110 | 432007 | 3803585 | 3803585 | 77 | 64 | 13 | 100% | 99.87% | 100% | 99.87% | 100% | 96.48% | 100% | 33.14% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 263294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-07-13 |  |  | 100% | 95.74% |  |  | -4.26% | 2023-11-30 | -262 | 0 | 110 | 432799 | 3810713 | 3810713 | 77 | 64 | 13 | 100% | 99.87% | 100% | 99.87% | 100% | 96.51% | 100% | 33.53% | Possibility of Variations affecting the project Completion | Variations if any, to be issued to the Contractor at the earliest | Client | Open | [8 empty] | Lack of manpower to address the open work fornt | Contractor to mobilize more manpower | Delay in delivery of materials | Contractor is delayed in delivery of materials which is impacting the works | Contractor must expedite the procurement process | [6 empty] | 23 | 17 | 2 | 13 |  | 8 | 8 | 0 | 8 |  |  | 15 | 11 | 3 | 10 |  | 224759024 | 38535714.01 | 192261304.74 | 192244304.74 | 192261304.74 | 17000 | 207294738.01 | Delay in t&c | Delay in finishes | Delay in MEP
PJ1 | 2023-07-20 |  |  | 100%
PJ1 | 2023-07-27 |  |  | 100%
PJ1 | 2023-08-03 |  |  | 100%
PJ1 | 2023-08-10 |  |  | 100%
PJ1 | 2023-08-17 |  |  | 100%
PJ1 | 2023-08-24 |  |  | 100%
PJ1 | 2023-08-31 |  |  | 100%
PJ1 | 2023-09-07 |  |  | 100%
PJ1 | 2023-09-14 |  |  | 100%
PJ1 | 2023-09-21 |  |  | 100%
PJ1 | 2023-09-28 |  |  | 100%
PJ1 | 2023-10-05 |  |  | 100%
PJ1 | 2023-10-12 |  |  | 100%
Formulas:
Forecast Completion = [Forecast Completion, row above]+7
Date = +[Date, row above]+7

## Sheet2
18 | 18 | 18 | 32 | 44 | 44 | 46 | 45 | 45 | 45 | 60 | 57 | 57 | 57 | 59 | 59 | 139 | 159 | 152 | 152 | 153 | 152 | 155 | 188 | 189 | 190 | 199 | 199 | 209 | 212 | 255 | 255 | 254 | 254 | 302 | 301 | 301 | 299 | 298 | 298 | 298 | 301 | 301 | 301 | 301 | 301 | 299 | 299 | 307 | 307 | 307 | 307 | 307 | 307 | 340 | 340 | 330 | 403 | 444 | 487 | 497 | 497 | 497 | 497 | 497 | 633 | 651 | 718 | 718 | 713 | 713 | 713 | 713 | 686 | 570 | 565 | 565 | 910 | 940 | 956 | 939 | 675 | 856 | 675 | 625 | 625 | 625 | 625 | 524 | 524 | 524 | 524 | 524 | 524 | 524 | 524 | 524 | 524 | 524 | 524 | 433 | 493 | 493 | 493 | 493 | 493 | 493 | 493 | 493 | 493 | 493 | 493 | 493 | 493 | 321 | 316 | 316 | 316 | 316 | 303 | 303 | 296 | 298 | 298 | 358 | 364 | 364 | 364 | 266 | 266 | 362 | 362 | 362 | 380 | 410 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 422 | 210 | 210 | 210 | 210 | 210 | 200 | 200 | 200 | 140 | 96 | 101 | 101 | 101 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 113 | 109 | 92 | 110 | 110
| 0 | 0 | -3 | -3 | -6 | -6 | -11 | -11 | -18 | -18 | -21 | -25 | -28 | -35 | -40 | -46 | -49 | -54 | -47 | -31 | -35 | -39 | -45 | -48 | -49 | -52 | -57 | -63 | -65 | -70 | -75 | -82 | -87 | -91 | -96 | -105 | -112 | -115 | -128 | -135 | -143 | -126 | -129 | -136 | -142 | -172 | -177 | -182 | -182 | -185 | -191 | -198 | -206 | -219 | -228 | -231 | -234 | -234 | -234 | -236 | -235 | -235 | -238 | -246 | -252 | -260 | -271 | -278 | -285 | -294 | -298 | -304 | -315 | -315 | -320 | -325 | -318 | -319 | -316 | -322 | -326 | -333 | -339 | -343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 7 | 3 | 1 | -2 | -7 | -9 | -11 | -17 | -24 | -31 | -38 | -45 | -52 | -61 | -68 | -75 | -81 | -86 | -91 | -98 | -105 | -111 | -118 | -125 | -131 | -138 | -143 | -149 | -150 | -156 | -161 | -167 | -174 | -181 | -185 | -192 | -199 | -206 | -213 | -219 | -226 | -234 | -241 | -247 | -252 | -259

## Discipline (hidden)
Discipline | Engineer Incharge
Adiminstration | Haytham
Mechanical | Joherto
Electrical | Artur
Civil | Buan
Architectural | Patrick
Irrigation | Reji
Telecom | Shaji
Security Systems | Wasim
Horticulture | Anandan
Health Safety | Shaji Nair
Contract Adminstration | Arjit
Cost/Finance | Richard
Façade Engineering | Gamal
Foul Sewer | Joherto
Hardscape | Buan
Landscaping | Anandan
Logistics | Haytham
Planning | Arjit
Plumbing | Joherto
Project Management | Arjit
Quality | Hayrettin
Utilities | Buan

## Document Types (hidden)
Document Type
Materials
Prequalification
Shop Drawings
Instructions
Letters
Non-conformance Reports
Design Calcuations
Detailed Designs
IFC
Method Statement