## Instructions
BUSINESS RESILIENCE PULSE CHECK
Improvement Plan Tracker
Corrective action tracking — companion to the Pulse Check After-Action Report
PURPOSE
This workbook is the working companion to the Improvement Plan in the After-Action Report (Appendix A). While the AAR records findings and recommendations, this tracker manages them to completion: one row per finding, with owner, dates, status, and progress notes.
HOW TO USE THIS WORKBOOK
1. After the After-Action Meeting, copy each finding from the AAR into the Improvement Plan sheet — one row per finding (F-01, F-02, ... then S-01, S-02 for strengths).
2. The facilitator provides the recommended timeframe based on severity; the client confirms the assigned Owner and Target date.
3. Update Status and Progress Notes at each review point: 30, 60, and 90 days after the exercise, and before the next exercise.
4. Severity, HSEEP Element, and Status columns use dropdown lists (see the Reference sheet for definitions).
5. Yellow cells are for you to fill in. The example row shows the expected format — replace it with your first real finding.
REVIEW SCHEDULE
30 days — status check on all Critical and High findings. 60 days — status check on all findings; escalate blocked items. 90 days — comprehensive progress review. Pre-next-exercise — outstanding items inform the next exercise's objectives.
REMEDIATION PRIORITY TIERS
Immediate (Critical): 0–30 days, weekly updates. Near-Term (High): 30–60 days, bi-weekly updates. Planned (Medium): 60–90 days, monthly updates. Opportunistic (Low): 90–180 days, quarterly updates. Maintain (Informational): ongoing, annual review.

## Improvement Plan
BUSINESS RESILIENCE PULSE CHECK
Improvement Plan — Corrective Action Tracking
One row per AAR finding. Yellow cells in the header block are inputs.
Client Organization: | [CLIENT NAME]
Exercise Date: | [DATE]
Scenario: | [SCENARIO TITLE]
AAR Reference: | [AAR date/version]
Tracker Version: | [Draft / Final]
Last Updated: | [DATE]
F# | Severity | Observation Summary | Corrective Action | HSEEP Element | Owner | Start | Target | Status | Progress Notes
F-01 | High | No documented escalation thresholds; participants could not identify when to engage executives or counsel. | Define escalation thresholds for all incident classification levels; document in the IR plan; brief all response team members. | Planning | COO | 2026-08-01 | 2026-09-15 | In Progress | EXAMPLE ROW — replace with your first finding. Draft thresholds in legal review.

## Reference
BUSINESS RESILIENCE PULSE CHECK
Reference Tables
Severity, HSEEP elements, status definitions, and priority tiers
SEVERITY LEVELS
Level | Definition | Action Window
Critical | Immediate, material threat to operations, life safety, regulatory obligations, or financial viability. Single point of failure with no workaround. | 0–30 days (Immediate)
High | Significant gap that materially weakens resilience. Capability exists but is critically incomplete, untested, or single-person dependent. | 30–60 days (Near-Term)
Medium | Meaningful gap that reduces effectiveness but would not likely cause complete failure. Informal or undocumented process. | 60–90 days (Planned)
Low | Minor gap or improvement opportunity. Capability functional but could be more efficient or better documented. | 90–180 days (Opportunistic)
Informational | Demonstrated strength that met or exceeded expectations. Maintain and reinforce. | Ongoing (Maintain)
HSEEP CAPABILITY ELEMENTS
Element | Definition | Example Actions
Planning | Developing or updating plans, policies, procedures, and agreements. | Update IR plan; develop communication plan; create succession documentation
Organization | Restructuring roles, responsibilities, authorities, and reporting. | Define escalation thresholds; assign incident commander; establish cross-training
Equipment | Acquiring, updating, or configuring tools, systems, and technology. | Implement isolated backups; deploy MFA; establish backup communication channel
Training | Developing and delivering training and awareness activities. | Media training for spokesperson; verification-procedure training for AP staff
Exercise | Planning and conducting future exercises to validate improvements. | Follow-up exercise in 6–12 months; focused communication walkthrough
STATUS DEFINITIONS
Status | Definition
Not Started | Acknowledged but work has not begun.
In Progress | Owner is actively working on the corrective action.
Complete | Fully implemented and validated.
Deferred | Intentionally postponed. Requires documented justification and a revised target date.
Blocked | Progress prevented by a dependency, resource constraint, or pending decision. Requires escalation.
Maintain | Used for strengths — the demonstrated capability is maintained through ongoing practice.