BUSINESS RESILIENCE PULSE CHECK

PC-701

Operations Manual

Delivery workflow, kickoff checklist, quality gates, closeout, and facilitator readiness

Internal Operations  |  Version 1.0  |  July 2026

# 1. The Delivery Workflow

The end-to-end workflow for every Pulse Check engagement. Each step lists the activity, the package document used, the owner, and the timeline. All quality gates in Section 3 apply.

ℹ GGUIDANCE: The Advisory Relationship Context The Pulse Check is the entry point into a recurring advisory relationship. Step 6 explicitly transitions from “engagement complete” to “advisory relationship active.” The findings don’t end at delivery , they become the roadmap for the relationship. Every touchpoint is earned by the findings, not manufactured by a sales calendar.

## Step 1: Sales and Qualification

| Activity | Document | Owner | Timeline |
| --- | --- | --- | --- |
| Prospect conversation with diagnostic positioning | Service One-Pager; Sales Playbook (01 - Sell) | Sales / Facilitator | As needed |
| Present the Pulse Check and pricing | Sales Playbook (01 - Sell) | Sales / Facilitator | As needed |
| Send proposal | Proposal Template (01 - Sell) | Sales / Facilitator | Within 5 BD of interest |
| Client accepts proposal | , | Client | Per proposal validity |

## Step 2: Engagement Setup

| Activity | Document | Owner | Timeline |
| --- | --- | --- | --- |
| Execute NDA, then SOW | Mutual Non-Disclosure Agreement; Statement of Work and Engagement Terms (02 - Contract) | Both parties | Before any work begins |
| Collect 50% deposit | Per SOW payment terms | Facilitator/Admin | Upon SOW execution |
| Complete kickoff checklist | Section 2 of this manual | Facilitator | Within 5 BD |
| Send intake packet | Client Intake Packet (03 - Plan) | Facilitator | Within 3 BD |
| Assign and brief observer | Observer Kit (05 - Deliver) | Facilitator/Manager | At kickoff |
| Populate planning timeline | Planning Workbook, Section 1 (03 - Plan) | Facilitator | At kickoff |

## Step 3: Planning and Scenario Development

| Activity | Document | Owner | Timeline |
| --- | --- | --- | --- |
| Review returned intake and documentation | Client Intake Packet responses | Facilitator | Upon receipt |
| Select scenario | Program Guide Section 5; 04 - Scenario Packages | Facilitator | Week 2 |
| Develop and agree objectives | Planning Workbook, Section 2 | Facilitator + Client | Week 2 |
| Customize scenario | Scenario package + Planning Workbook, Section 6 | Facilitator | Weeks 2–4 |
| Finalize participant list | Planning Workbook, Section 3 | Client coordinator | Week 3 |
| Send invitations (Form B attached) | Planning Workbook appendix; Pre-Exercise Forms (02 - Contract) | Client coordinator | Week 3 (≥10 BD before) |
| Obtain client sign-off | Pre-Exercise Forms, Form A | Client coordinator | ≥5 BD before exercise |
| Complete logistics | Planning Workbook, Section 5 | Both | Week 4 |

## Step 4: Exercise Delivery

| Activity | Document | Owner | Timeline |
| --- | --- | --- | --- |
| Day-of setup and QA | Section 3 Phase 3 gates; Planning Workbook, Section 5 | Facilitator | Morning of |
| Collect sign-ins and Form B agreements | Exercise Day Forms; Pre-Exercise Forms (Form B) | Observer / Facilitator | On arrival |
| Deliver the exercise | Facilitator Guide; customized scenario package | Facilitator | 2–3 hours |
| Document observations | Observer Kit, Part 2 | Observer | Throughout |
| Hot wash and feedback forms | Facilitator Guide; Exercise Day Forms | Facilitator | Final 25 min |
| Facilitator–observer debrief | Observer Kit | Both | Within 2 hours |

## Step 5: Post-Exercise Deliverables

| Activity | Document | Owner | Timeline |
| --- | --- | --- | --- |
| Compile observer notes | Observer Kit, Part 2 | Observer | +1 BD |
| Compile participant feedback | Exercise Day Forms responses | Facilitator | +3 BD |
| Write draft AAR | Pulse Check AAR Template (06 - Report); Severity and Finding Standards + Sample Findings Library (00 - Quality Standards) | Facilitator | +10 BD |
| Peer review (strongly recommended) | Severity and Finding Standards, Section 5 | Peer reviewer | +10 to +13 BD |
| Prepare Executive Summary | Executive Summary Template (06 - Report) | Facilitator | +13 BD |
| Deliver draft package | AAR + Executive Summary | Facilitator | +15 BD |
| After-Action Meeting; client comments | Draft AAR; Improvement Plan appendix | Both | By +30 BD |
| Finalize and deliver full package | Final AAR; Compliance Evidence Package; Improvement Plan Tracker.xlsx | Facilitator | +30 BD |
| Collect final 50% payment | Per SOW payment terms | Admin | Upon draft delivery per SOW |

## Step 6: Closeout and Advisory Relationship Activation

| Activity | Document | Owner | Timeline |
| --- | --- | --- | --- |
| Complete closeout checklist | Section 4 of this manual | Facilitator | +35 BD |
| Update delivery log | Facilitator Delivery Log.xlsx (this folder) | Facilitator | +35 BD |
| Document lessons learned | Section 4 of this manual | Facilitator | +35 BD |
| Map findings to your service capabilities | Program Guide, Section 7 | Facilitator | +35 BD |
| Schedule 30/60/90-day advisory check-ins | Program Guide, Section 6 Phase 6 | Facilitator | +35 BD |
| Send renewal proposal | Annual Renewal Proposal (this folder) | Facilitator | 60–90 days after delivery |

# 2. Engagement Kickoff Checklist

Complete all items within the first 5 business days after SOW execution. File the completed checklist in the engagement record.

## Administrative

☐  SOW and Engagement Terms fully executed and filed

☐  NDA fully executed and filed

☐  Deposit invoice sent (per SOW payment terms)

☐  Deposit received and confirmed

☐  Engagement folder created (legal / planning / materials / delivery / post-exercise)

☐  Calendar holds placed for exercise date, planning meetings, and AAR deadlines

## Client Communication

☐  Kickoff call scheduled or completed

☐  Client Intake Packet sent to coordinator with return dates (Section A: 10 BD, Section B: 15 BD)

☐  Cancellation terms (SOW Exhibit A) acknowledged by client

☐  Planning timeline populated and shared with the coordinator

## Team Assignment

☐  Lead facilitator confirmed and has completed the Facilitator Training Plan

☐  Observer confirmed and briefed on engagement scope

☐  Peer reviewer identified if available (see Severity and Finding Standards for review options)

## Planning Initiation

☐  Scenario type tentatively identified from SOW scope

☐  First planning meeting date confirmed with client

☐  Available client documentation reviewed (prior reports, IR plan, org chart)

☐  Risk factors identified (scheduling, participant availability, client responsiveness)

# 3. Quality Gates

Every engagement must pass these gates. An engagement that fails a mandatory gate must be remediated before proceeding.

✓ QQUALITY STANDARD: Quality Is Not Optional These standards are the minimum floor for every engagement. They protect the program’s reputation, the practitioner’s credibility, and the client’s investment. Cutting corners on quality is how practices die.

## Phase 1: Pre-Engagement (before the exercise date is confirmed)

☐  SOW and NDA executed and filed

☐  Intake questionnaire returned and reviewed

☐  Facilitator assigned and has completed the Facilitator Training Plan

☐  Observer assigned (mandatory ,  no exceptions)

☐  Exercise objectives developed and approved by the client

☐  Scenario selected and customization scope defined

☐  Planning timeline shared with the client

☐  Deposit received

## Phase 2: Pre-Exercise (at least 5 business days before)

☐  Participant list finalized and reviewed for functional-area coverage

☐  Key stakeholder availability confirmed (absence framework applied if needed)

☐  Scenario customization complete ,  no [CUSTOMIZE] tags or placeholder text remain

☐  Pre-Exercise Forms Form A signed and returned

☐  Invitations sent to all participants with Form B attached

☐  Logistics confirmed per the Planning Workbook checklist

☐  Facilitator guide annotated with client-specific probe questions

☐  Observer template pre-populated with objectives and participant names

☐  Real Incident During Exercise Protocol reviewed by facilitator and observer

## Phase 3: Day-Of (before the exercise begins)

☐  Room or virtual platform confirmed and functional

☐  All materials staged (Participant Guides, forms, inject cards, presentation)

☐  Facilitator–observer alignment completed

☐  Sign-in sheet ready; Form B copies ready for collection

☐  Client coordinator confirms participants are attending

## Phase 4: Post-Exercise (before the draft goes to peer review)

☐  Sign-in sheet and all Form B agreements collected

☐  Observer notes compiled within 24 hours

☐  Feedback forms collected and compiled within 3 business days

☐  Facilitator–observer debrief completed within 24 hours

☐  Every finding follows the four-part structure

☐  Every severity rating calibrated per Severity and Finding Standards

☐  Minimum 3 strength findings included

☐  AAR follows the mandatory section structure, scope limitation statement intact

☐  No copy-paste findings; no blame language; Executive Summary passes the “CEO reads only this” test

## Phase 5: Pre-Delivery (before the client sees the draft)

☐  Peer review completed (see Severity and Finding Standards for options including AI-assisted review)

☐  All peer review feedback addressed or documented as resolved

☐  Finding numbers and ratings consistent across the AAR, findings matrix, and Improvement Plan

☐  All template instruction callouts removed from client deliverables

☐  Draft clearly marked DRAFT; delivered within 15 business days of the exercise

## Phase 6: Post-Delivery

☐  Client comments received and incorporated; Improvement Plan owners and dates confirmed at the After-Action Meeting

☐  Final AAR marked FINAL and delivered within 30 business days of the exercise

☐  Compliance Evidence Package assembled and delivered

☐  Closeout checklist (Section 4) completed

☐  Client satisfaction feedback collected; lessons learned documented; delivery log updated

# 4. Post-Engagement Closeout Checklist

Complete all items within 10 business days of final AAR delivery.

## Deliverables and Finance

☐  All deliverables confirmed received by the client and marked FINAL

☐  Final invoice sent; all payments received

☐  Travel expenses submitted and reimbursed (if applicable)

☐  Actual hours vs. estimate compared; engagement profitability documented

## Data Handling

☐  Client-provided documentation stored securely per the SOW data handling terms

☐  Retention period start date recorded; destruction date calendared

☐  Observer notes destruction completed and dated after final AAR acceptance and peer review closure

☐  Exercise materials archived or destroyed per the SOW terms

## Quality Documentation

☐  Facilitator Delivery Log updated with engagement details and feedback scores

☐  Lessons learned documented (what worked, what to change, scenario notes)

☐  Peer review feedback filed

☐  Any quality issues documented for program improvement

## Advisory Relationship

☐  Thank-you communication sent to the client coordinator

☐  Findings reviewed against your service capabilities (Program Guide, Section 7)

☐  30/60/90-day advisory check-ins scheduled

☐  Next exercise recommendation documented (from AAR Conclusion)

☐  Client added to the renewal pipeline; renewal proposal timing identified (60–90 days)

☐  Testimonial or case study opportunity discussed (with client permission)

# 5. Facilitator Readiness and Training

## 5.1 Foundational Requirements (before first delivery)

| Requirement | Detail |
| --- | --- |
| FEMA IS-120.c , An Introduction to Exercises | Recommended self-study. Free at training.fema.gov (~3 hours). Provides useful HSEEP context but is not required before your first delivery. |
| FEMA IS-130 , Exercise Evaluation and Improvement Planning | Recommended self-study. Free (~2 hours). Useful for understanding evaluation methodology but not required before your first delivery. |
| Program document review | Read the Program Guide, Severity and Finding Standards, Sample Findings Library, Pulse Check AAR Template, and Facilitator Guide. |
| Internal dry run | Facilitate a full Pulse Check on your own team (minimum 5–6 participants) with a colleague as observer, using GS-1c or GS-3. |
| Practice AAR | Write a complete practice AAR from the dry run. Having it reviewed by an AI tool is a reasonable starting point for calibrating your writing , but AI review alone is not a substitute for eventual human peer review as your practice matures. |

ℹ GGUIDANCE: The Dry Run Pays Twice It gives the facilitator practice in a low-stakes environment, and it genuinely tests your own organization’s preparedness. Document the dry run, the practice AAR, and the review feedback in the Facilitator Delivery Log.

## 5.2 Core Competencies

| Competency | Description | Assessed Through |
| --- | --- | --- |
| HSEEP methodology | Exercise design, evaluation, and improvement planning per HSEEP doctrine | Self-study; dry run; ongoing practice |
| Scenario customization | Tailoring scenarios to client industry, structure, and regulatory environment | Practice AAR; customization checklist compliance |
| Adaptive facilitation | Guiding discussion with judgment and probe questions rather than rigid scripts | Client feedback; observer feedback |
| Observation and analysis | Translating exercise observations into calibrated, actionable findings | AAR quality; peer review calibration |
| Professional writing | Producing AARs and summaries that meet the writing standards | Practice AAR; peer review feedback |
| Client management | Managing expectations, navigating sensitive findings, maintaining relationships | Client and coordinator feedback |
| Quality discipline | Consistent adherence to the observer mandate, peer review, and quality gates | Delivery log; QA compliance |

## 5.3 Ongoing Development

- Annual refresh: re-read the quality standards documents and complete at least one peer review per year.

- Continuous improvement: review lessons learned after every delivery.

- Peer community: participate in a facilitator peer review network for calibration and development.

- Industry awareness: stay current with emerging threats, regulatory changes, and emerging scenario types.

- Professional development: FEMA’s IS-120.c, IS-130, and the Master Exercise Practitioner Program (MEPP) are excellent resources as your practice matures and you want deeper methodological grounding.